|  |  |  |
| --- | --- | --- |
| **NATIONS**  **UNIES** | | **EP** |
| UNEP | **Programme des**  **Nations Unies pour**  **l’environnement** | Distr.  GÉNÉRALE  UNEP/OzL.Pro/ExCom/87/4  22 juin 2021  FRANÇAIS  ORIGINAL : ANGLAIS |

COMITÉ EXÉCUTIF

 DU FONDS MULTILATÉRAL AUX FINS   
 D’APPLICATION DU PROTOCOLE DE MONTRÉAL  
Quatre-vingt-septième réunion

Montréal, 28 juin – 2 juillet 2021[[1]](#footnote-1)

**RAPPORT SUR LES SOLDES ET DISPONIBILITÉ DES RESSOURCES**

**Introduction**

1. Ce document présente un résumé des ajustements financiers communiqués par les agences bilatérales et d’exécution, et approuvés par le Secrétariat. Il comprend des données statistiques[[2]](#footnote-2) de tous les projets dont les soldes ont été détenus pendant plus de 12 mois après l’achèvement du projet, conformément aux décisions 28/7 et 56/2(c). Il examine les soldes à restituer provenant de projets au titre du suivi donné à des décisions les concernant (appelés projets « soumis à décision » dans le présent document). Il indique au Comité exécutif le niveau des ressources disponibles en liquidités enregistrées dans le document État des contributions et décaissements[[3]](#footnote-3) conformément à la décision 41/92(b), et présente une recommandation.
2. Le présent document comprend aussi les quatre annexes suivantes :

Annexe I Sommes détenues par les agences bilatérales et d’exécution pour des projets achevés

Annexe II Sommes détenues par les agences bilatérales et d’exécution pour des projets soumis à décision

Annexe III Sommes détenues par les agences bilatérales et d’exécution pour des projets financés à l’aide de contributions supplémentaires

Annexe IV Fonds restitués par les agences bilatérales et d’exécution provenant de projets achevés, de projets soumis à décision, et de projets financés par des contributions volontaires supplémentaires

# Les Annexes I, II et III fournissent des explications sur les retards intervenus dans le décaissement des montants engagés ou la restitution des montants non engagés.

**Fonds à restituer à la 87e réunion**

# Le montant total des fonds à restituer s’élève à 2 315 105 $US (soit 6 747 $US par les agences bilatérales et 2 308 358 $US par les agences d’exécution) provenant de projets achevés, de projets soumis à décision, et de projets financés par des contributions supplémentaires.

Fonds devant être restitués par les agences d’exécution

# Le total des fonds devant être restitués par les agences d’exécution s’élève à 2 308 358 $US, comme l’indique le tableau 1.

# **Tableau 1. Fonds à restituer à la 87e réunion par les agences d’exécution ($US)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Agence** | **Coûts de projet** | **Coût d’appui d’agence** | **Coût total** |
| PNUD | 58 511 | 4 199 | 62 710 |
| PNUE | 1 867 022 | 148 337 | 2 015 359 |
| ONUDI | 214 743 | 15 546 | 230 289 |
| **Total** | 2 140 276 | 168 082 | 2 308 358 |

# Le tableau 2 présente des informations sur les soldes encore détenus par les agences d’exécution pour des projets achevés, des projets soumis à décision ou des projetsfinancés par des contributions volontaires supplémentaires.

**Tableau 2. Soldes encore détenus par les agences d’exécution pour des projets achevés, des projets soumis à décision ou des projets financés par des contributions volontaires supplémentaires.**

| **Année d’achèvement** | **PNUD** | | **PNUE** | | **ONUDI** | | **Total** | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Nombre** | **($US)** | **Nombre** | **($US)** | **Nombre** | **($US)** | **Nombre** | **($US)** |
| **Projets achevés depuis plus de 2 ans** | | | | | | | | |
| 2016 | 0 | 0 | 1 | 68 727 | 0 | 0 | 1 | 68 727 |
| 2017 | 0 | 0 | 3\* | 8 591 | 0 | 0 | 3 | 8 591 |
| 2018 | 0 | 0 | 3 | 32 054 | 0 | 0 | 3 | 32 054 |
| 1er janvier au  31 mai 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| **Total partiel** | **0** | **0** | **7** | **109 372** | **0** | **0** | **7** | **109 372** |
| **Projets achevés depuis moins de deux ans** | | | | | | | | |
| 1er juin au  31 décembre 2019 | 15 | 4 507 300 | 7 | 444 737 | 4 | 14 134 | 26 | 4 966 171 |
| **Total partiel** | **15** | **4 507 300** | **7** | **444 737** | **4** | **14 134** | **26** | **4 966 171** |
| **Total** | **15** | **4 507 300** | **14** | **554 109** | **4** | **14 134** | **33** | **5 075 543** |
| **Projets soumis à décision (en cours)** | | | | | | | | |
|  | 1 | 160 869 | 4 | 293 788 | 0 | 0 | 5 | 454 657 |
| **Contributions volontaires supplémentaires** | | | | | | | | |
|  | 0 | 0 | 1 | 10 110 | 1 | 2 132 | 2 | 12 242 |
| **Total général** | **16** | **4 668 169** | **19** | **858 006** | **5** | **16 266** | **40** | **5 542 441** |

\* Y compris un projet d’enquête sur les solutions de remplacement aux SAO

Fonds devant être restitués par les agences bilatérales

# Le total des fonds devant être restitués par les agences bilatérales s’élève à 6 747 $US, soit 6 247 $US, plus coûts d’appui d’agence de 500 $US pour la France.

**Disponibilité des ressources**

# Le document sur l’État des contributions et des décaissements indique au 9 juin 2021 un solde disponible d’un montant de 334 427 526 $US. Le solde total restitué par les agences bilatérales et d’exécution à la 87e réunion s’élève à 2 308 358 $US, faisant que le niveau de ressources disponibles pour les approbations lors de cette réunion est de 336 735 884 $US.

**Observations du Secrétariat**

# Le Secrétariat a rappelé aux agences bilatérales et d’exécution que les soldes des projets soumis à décision et des projets achevés depuis un an ou plus doivent être restitués dès que possible au Fonds multilatéral.

# Considérant que le montant total du financement demandé pour des projets et activités soumis à la 87e réunion s’élève à 22 042 297 $US, coûts d’appui d’agence compris, les ressources disponibles sont suffisantes pour les approbations de cette réunion.

**Recommandations**

# Le Comité exécutif pourrait envisager :

* 1. De prendre note :

1. Du Rapport sur les soldes et la disponibilité des ressources, figurant dans le document UNEP/OzL.Pro/ExCom/87/4 ;
2. Que le montant net des fonds restitués à la 87e réunion par les agences d’exécution s’élève à 2 308 358 $US, soit 58 511 $US plus coûts d’appui d’agence de 4 199 $US par le PNUD ; 1 867 022 $US plus coûts d’appui d’agence de 148 337 $US par le PNUE ; et 214 743 $US plus coûts d’appui d’agence de 15 546 $US par l’ONUDI ;
3. Que le PNUE détient un solde de 109 372 $US, coûts d’appui d’agence compris, pour sept projets achevés depuis plus de deux ans, incluant un projet d’enquête sur les solutions de remplacement aux SAO avec un solde de 434 $US, coûts d’appui d’agence compris, et 10 110 $US, coûts d’appui d’agence compris, pour un projet financé à l’aide de contributions volontaires supplémentaires ;
4. Que l’ONUDI détient un solde de 2 132 $US, coûts d’appui d’agence compris, pour un projet financé à l’aide de contributions volontaires supplémentaires ; et
5. Que le montant net restitué par le gouvernement de la France à la 87e réunion s’élève à 6 247 $US, plus 500 $US de coûts d’appui d’agence.

## De demander :

* + 1. Aux agences bilatérales et d’exécution de procéder au décaissement ou d’annuler les sommes engagées et non engagées qui ne sont pas nécessaires aux projets achevés et à ceux achevés « par décision du Comité exécutif », et de restituer les soldes correspondants à la 88eréunion ;

### Au PNUE de restituer à la 88e réunion le solde d’un projet d’enquête sur les solutions de remplacement aux SAO achevé il y a plus de deux ans, conformément à la décision 80/75(c)(i), ainsi que le solde d’un projet achevé financé par des contributions volontaires supplémentaires ;

### Au PNUE de procéder au décaissement ou d’annuler ses engagements pour les six projets restants, achevés depuis plus de deux ans, et de restituer les soldes à la 88e réunion ;

### À l’ONUDI de restituer à la 88e réunion le solde d’un projet achevé financé à l’aide de contributions volontaires supplémentaires ; et

### Au Trésorier d’effectuer le suivi auprès du gouvernement de la France concernant la restitution, en liquidités, du montant de 6 747 $US dont il est question ci-dessus à l’alinéa (a)(v).

**Annex I**

**COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS**

| **Code** | **Project title** | **Date completed (Actual)** | **Approved funding plus adjustments as of 31 December 2019 (US $)** | **Funds disbursed as of**  **87th meeting (US $)** | **Balances committed as per 87th meeting (US $)** | **Balances not-committed as per 87th meeting (US $)** | **Support cost on balances committed & not committed as per 87th meeting (US $)** | **Why any balances could not be returned?** | **When they could be returned?** | **Project subject to decision** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDP** | | | | | | | | | | |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | Dec-19 | 3,000,000 | 1,979,026 | 1,020,974 |  | 76,573 |  |  | 84/32(b)(iii) and 85/5(a)(ii) |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | Dec-19 | 1,470,700 | 437,803 | 1,032,897 |  | 77,468 |  |  | 84/32(b)(iii) and 85/5(a)(ii) |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,475 | 5,382 |  | 377 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,857,930 | 142,070 |  | 10,655 |  |  | 82/72(a)(iv) |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 288,322 | 428,078 |  | 32,106 |  |  | 82/72(a)(iv) |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 35,639 | 24,211 |  | 2,179 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 343,303 | 3,891 |  | 272 |  |  |  |
| MDV/REF/76/DEM/30 | Demonstration project for HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector | Dec-19 | 141,000 | 139,472 | 1,528 |  | 138 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,456,632 | 343,368 |  | 25,753 |  |  | 84/22(b) and (c) |
| MEX/PHA/75/INV/178 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 1,122,503 | 0 | 1,122,503 |  | 84,188 |  |  | 84/22(b) and (c) |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| **TOTAL UNDP** |  |  |  |  | **4,192,698** |  | **314,602** |  |  |  |
| **UNEP** | | | | | | | | | | |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Dec-19 | 375,000 | 342,491 | 27,696 |  | 3,600 |  |  | 83/37(c) and 85/18(b) |
| BAH/PHA/68/TAS/28 | HCFC phase-out management plan (stage I, first tranche) (policy, refrigeration servicing, monitoring and verification) | Dec-18 | 120,000 | 116,882 | 3,118 |  | 405 |  |  |  |
| CHI/PHA/76/TAS/193 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | Dec-17 | 53,000 | 52,493 | 507 |  | 66 |  |  | 76/45(a)(iii) and 81/14(b)(ii) |
| GBS/PHA/71/TAS/17 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 52,000 | 29,079 | 22,921 |  | 2,980 |  |  |  |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | Dec-19 | 9,974,259 | 8,055,902 | 307,619 |  | 24,610 |  |  |  |
| GUY/PHA/75/TAS/27 | HCFC phase-out management plan (stage II, first tranche) | Oct-19 | 55,500 | 50,000 | 5,500 |  | 715 |  |  |  |
| HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 40,000 | 19,591 | 20,409 |  | 2,653 |  |  |  |
| IRQ/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Dec-18 | 115,000 | 110,266 | 4,734 |  | 582 |  |  |  |
| KUW/PHA/52/TAS/10 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Jan-16 | 232,912 | 172,092 | 60,820 |  | 7,907 |  |  | 70/7(b)(ii)a. |
| KUW/REF/75/TAS/29 | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | Jun-18 | 27,223 | 6,679 | 20,544 |  | 2,671 |  |  | 82/24(c)(ii) and 83/38(b) |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | Dec-19 | 88,748 | 69,423 | 19,325 |  | 0 |  |  |  |
| PAR/PHA/63/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | Jun-17 | 146,500 | 139,788 | 6,712 |  | 873 |  |  |  |
| PAR/SEV/77/INS/36 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | Dec-19 | 85,000 | 78,292 | 6,708 |  | 0 |  |  |  |
| STL/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | Dec-17 | 35,000 | 31,609 | 384 |  | 50 |  |  | 80/75(c)(i) |
| **TOTAL UNEP** |  |  |  |  | **506,997** |  | **47,112** |  |  |  |
| **UNIDO[[4]](#footnote-4)** | | | | | | | | | | |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | Jul-19 | 345,000 | 339,533 | 5,467 |  | 383 | 2 | 88th meeting | 84/24(b) |
| MLW/PHA/77/INV/40 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 60,000 | 59,885 | 115 |  | 10 | 2 | 88th meeting |  |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 200,000 | 199,292 | 708 |  | 53 | 2 | 88th meeting |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 2 | 88th meeting |  |
| **TOTAL UNIDO** |  |  |  |  | **13,207** |  | **927** |  |  |  |

**Annex II**

**COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS**

| **Code** | **Project title** | **Financial date of completion per decision** | **Approved funding plus adjustments as of 31 December 2019 (US $)** | **Funds disbursed as of**  **87th meeting (US $)** | **Balances committed as per 87th meeting (US $)** | **Balances not- committed as per 87th meeting (US $)** | **Support cost on balances committed and not-committed as per 87th meeting (US $)** | **Why any balances could not be returned?** | **When they could be returned?** | **Project subject to decision** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDP** | | | | | | | | | | |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,340,255 | 150,345 |  | 10,524 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| **TOTAL UNDP** |  |  |  |  | **150,345** |  | **10,524** |  |  |  |
| **UNEP** | | | | | | | | | | |
| QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 87th meeting | 105,000 | 38,955 | 66,045 |  | 8,586 |  |  |  |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 165,806 | 48,750 |  | 6,039 |  |  |  |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 87th meeting | 56,726 | 4,014 | 39,000 |  | 4,832 |  |  |  |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 14,509 | 107,250 |  | 13,286 |  |  |  |
| **TOTAL UNEP** |  |  |  |  | **261,045** |  | **32,743** |  |  |  |

**Annex III**

**COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **CODE** | **Project title** | **Financial date of completion per decision** | **Approved funding plus adjustments as of 31 December 2019 (US $)** | **Funds disbursed as of 87th meeting (US $)** | **Balances committed as per 87th meeting (US $)** | **Balances not- committed as per 87th meeting (US $)** | **Support cost on balances committed and not-committed as per 87th meeting (US $)** | **Why any balances could not be returned?** | **When they could be returned?** | **Project subject to decision** |
| **UNEP** | | | | | | | | | | |
| ZIM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down |  | 150,000 | 140,551 | 9,449 |  | 661 |  |  |  |
| **TOTAL UNEP** |  |  |  |  | **9,449** |  | **661** |  |  |  |
| **UNIDO[[5]](#endnote-2)** | | | | | | | | | | |
| LEB/REF/80/PRP/01+ | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 85th meeting | 30,000 | 28,008 | 1,992 |  | 139 | 2 | 88th meeting | 84/2(b)(ii) |
| **TOTAL UNIDO** |  |  |  |  | **1,992** |  | **139** |  |  |  |

i\*: 2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing; 5: Funds were not transferred

**Annex IV**

**DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES**

| **Code** | **Project title** | **Project costs returned (US $)** | **Agency support costs (US $)** | **Total (US $)** |
| --- | --- | --- | --- | --- |
| COL/PHA/75/TAS/94 | HCFC phase-out management plan (stage II, first tranche) (technical assistance for fire protection sector) | 2 | 0 | 2 |
| COS/REF/57/PRP/41 | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | 4,883 | 366 | 5,249 |
| COS/REF/74/PRP/51 | Preparation of a demonstration project for the transition of HCFC-22-based refrigerant unit to NH3 system in cold chambers | 1 | 0 | 1 |
| GHA/SEV/76/INS/41 | Extension of the institutional strengthening project (phase XII: 1/2017-12/2018) | 3,395 | 238 | 3,633 |
| PAK/SEV/77/INS/96 | Extension of the institutional strengthening project (phase IX: 4/2017-3/2019) | 569 | 40 | 609 |
| PAN/SEV/75/INS/42 | Extension of institutional strengthening project (phase VII: 12/2015-11/2017) | 184 | 13 | 197 |
| STK/PHA/64/TAS/16 | HCFC phase-out management plan (stage I, first tranche) | 58 | 5 | 63 |
| TLS/PHA/72/PRP/11 | Preparation of a HCFC phase-out management plan (stage II) | 5,000 | 350 | 5,350 |
| TLS/PHA/80/INV/18 | HCFC phase-out management plan (stage I, third tranche) | 4,030 | 363 | 4,393 |
| TRI/PHA/64/INV/26 | HCFC phase-out management plan (foam sector) (stage I, first tranche) | -547 | -41 | -588 |
| TRI/SEV/79/INS/34 | Extension of the institutional strengthening project (phase IX: 1/2018-12/2019) | 381 | 27 | 408 |
| **Total completed projects** |  | **17,956** | **1,360** | **19,316** |
| DOM/REF/80/PRP/01+ | Project preparation for conversion from HFC-134a to HC-290 in the manufacture of commercial refrigerators at Farco | 18,428 | 1,290 | 19,718 |
| EGY/FOA/80/PRP/01+ | Project preparation for conversion from HFC-134a to HFO-1234ze and other liquid HFOs in the manufacture of polyurethane foam and spray foam | 12,036 | 843 | 12,879 |
| ZIM/REF/80/PRP/02+ | Project preparation for elimination of HFC-134a in the manufacture of domestic refrigerators at Capri | 10,091 | 706 | 10,797 |
| **Total “additional voluntary contributions” projects** |  | **40,555** | **2,839** | **43,394** |
| **TOTAL UNDP** |  | **58,511** | **4,199** | **62,710** |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 4,813 | 626 | 5,438 |
| BHU/SEV/79/INS/27 | Extension of institutional strengthening project (phase VII: 12/2017-11/2019) | 336 | 0 | 336 |
| CHI/PHA/73/TAS/185 | HCFC phase-out management plan (stage I, third tranche) | 248 | 32 | 280 |
| CPR/PHA/74/TAS/559 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector including enabling programme) | 5,392 | 603 | 5,995 |
| DOM/PHA/69/TAS/52 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 8,816 | 1,146 | 9,962 |
| ECU/SEV/76/INS/62 | Extension of institutional strengthening project (phase VI: 5/2016-4/2018) | 23,774 | 0 | 23,774 |
| GLO/SEV/80/TAS/341 | Compliance Assistance Programme: 2018 budget | 158,314 | 12,665 | 170,979 |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | 1,610,738 | 128,859 | 1,739,597 |
| MEX/PHA/77/TAS/184. | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 1,694 | 220 | 1,914 |
| PAN/PHA/70/TAS/35 | HCFC phase-out management plan (stage I, second tranche) | 2,017 | 262 | 2,279 |
| PAN/PHA/74/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 1,863 | 242 | 2,105 |
| PER/PHA/68/TAS/47 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | 7,091 | 922 | 8,013 |
| PHI/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 9,651 | 0 | 9,651 |
| **Total completed projects** |  | **1,834,746** | **145,578** | **1,980,324** |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 19,118 | 2,368 | 21,486 |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 136 | -987 | -851 |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 8,641 | 1,070 | 9,711 |
| **Total “by decision” projects** |  | **27,895** | **2,452** | **30,347** |
| GHA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 575 | 40 | 615 |
| KAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,082 | 146 | 2,228 |
| LES/SEV/80/TAS/04+ | Enabling activities for HFC phase-down | 468 | 33 | 501 |
| TON/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 1,256 | 88 | 1,344 |
| **Total “additional voluntary contributions” projects** |  | **4,381** | **307** | **4,688** |
| **TOTAL UNEP** |  | **1,867,022** | **148,337** | **2,015,359** |
| ARG/PHA/80/TAS/186 | HCFC phase-out management plan (stage II, first tranche) (monitoring and reporting of HCFC-22 production) | 1,705 | 119 | 1,824 |
| ASP/REF/76/DEM/60 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 3,550 | 249 | 3,799 |
| BDI/PHA/65/INV/29 | HCFC phase-out management plan (stage I, first tranche) | 152 | 14 | 166 |
| BEN/PHA/76/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 51 | 4 | 55 |
| ECU/PHA/82/INV/70 | HCFC phase-out management plan (stage I, fourth tranche) | 171 | 12 | 183 |
| ECU/PHA/82/PRP/68 | Preparation of a HCFC phase-out management plan (stage II) | 67 | 5 | 72 |
| EGY/REF/75/TAS/127 | Feasibility study addressing district cooling | 2,435 | 219 | 2,654 |
| GBS/PHA/77/INV/21 | HCFC phase-out management plan (stage I, third tranche) | 229 | 20 | 249 |
| GUA/PHA/81/INV/51 | HCFC phase-out management plan (stage I, fourth tranche) | 169 | 13 | 181 |
| GUA/PHA/82/PRP/55 | Preparation of a HCFC phase-out management plan (stage II) | 82 | 6 | 88 |
| MDN/PHA/79/INV/39 | HCFC phase-out management plan (phase I, seventh tranche) | 70 | 5 | 75 |
| MEX/PRO/83/PRP/192 | Project preparation for the control of HFC-23 by-product emissions in the HCFC production sector | 307. | 21 | 328 |
| MEX/SEV/79/INS/186 | Extension of institutional strengthening project (phase XIII: 7/2017-6/2019) | 328 | 22 | 350 |
| MLW/PHA/81/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | 270 | 19 | 289 |
| MOG/PHA/75/INV/11 | HCFC phase-out management plan (stage I, third tranche) | 729 | 55 | 784 |
| MOR/FOA/75/DEM/74 | Demonstration of the use of low cost pentane foaming technology for the conversion to non-ODS technologies in polyurethane foams at small- and medium-sized enterprises | 4,303 | 301 | 4,604 |
| NIR/PHA/71/INV/136 | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | 1,082 | 81 | 1,163 |
| QAT/SEV/79/INS/22 | Renewal of institutional strengthening project (phase IV: 8/2017-7/2019) | 29,123 | 2,038 | 31,161 |
| SAU/FOA/76/DEM/27 | Demonstration project for the phase-out of HCFCs by using HFO as foam blowing agent in the spray foam applications in high ambient temperatures | 201 | 19 | 220 |
| SUD/PHA/80/INV/42 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 150 | 10 | 160 |
| TUN/FOA/77/PRP/72 | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | 33,747 | 2,363 | 36,110 |
| TUN/PHA/72/INV/58 | HCFC phase-out management plan (stage I, first tranche) (solvent sector plan) | 9,465 | 662 | 10,127 |
| TUR/PHA/75/INV/108 | HCFC phase-out management plan (stage I, second tranche) (technical assistance for small and medium enterprises in the foam sector) | 22,029 | 1,540 | 23,569 |
| URT/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 152 | 11 | 163 |
| YUG/PHA/82/TAS/49 | Verification report on the implementation of the HCFC phase-out management plan | 438 | 39 | 477 |
| **Total completed projects** |  | **111,003** | **7,848** | **118,851** |
| CPR/ARS/56/INV/473 | Sector plan for phase-out of CFCs consumption in MDI sector | 15,099 | 1,132 | 16,231 |
| QAT/PHA/65/INV/18 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 59,334 | 4,450 | 63,784 |
| QAT/PHA/65/INV/19 | HCFC phase-out management plan (stage I, first tranche) (sector conversion from HCFC-142b/HCFC-22 in the production of extruded polystyrene insulation boards to low GWP isobutene at Qatar Insulation, Orient Insulation and Al Kawthar Insulation) | 12,927 | 969 | 13,896 |
| **Total “by decision” projects** |  | **87,360** | **6,551** | **93,911** |
| CPR/FOA/81/PRP/05+ | Preparation for converting from HFC-134a to HFOs+CO2 with gluing technology in an extruded polystyrene foam manufacturer | 16,379 | 1,147 | 17,526 |
| MEX/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 1 | **0** | **1** |
| **Total “additional voluntary contributions” projects** |  | **16,380** | **1,147** | **17,527** |
| **TOTAL UNIDO** |  | **214,743** | **15,546** | **230,289** |
| TUN/PHA/76/INV/70 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 6,247 | 500 | 6,747 |
| **TOTAL FRANCE** |  | **6,247** | **500** | **6,747** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |

1. Des réunions et un processus d’approbation en période intersessions auront lieu en ligne en juin et juillet 2021 à cause du coronavirus (COVID-19) [↑](#footnote-ref-1)
2. Les données présentées s’appuient sur le format de rapport élaboré conformément à la décision 31/2. [↑](#footnote-ref-2)
3. UNEP/OzL.Pro/ExCom/87/3. [↑](#footnote-ref-3)
4. 2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5 project is ongoing; 6 Funds were not transferred. [↑](#footnote-ref-4)
5. [↑](#endnote-ref-2)