|  |  |  |
| --- | --- | --- |
| **UNITED NATIONS** | | **EP** |
|  | **United Nations**  **Environment**  **Programme** | Distr.  GENERAL  28 October 2021  ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF  
 THE MULTILATERAL FUND FOR THE  
 IMPLEMENTATION OF THE MONTREAL PROTOCOL  
Eighty-eighth Meeting

Montreal, 15-19 November 2021[[1]](#footnote-1)

CONSOLIDATED PROGRESS REPORT AS AT 31 DECEMBER 2020

# The consolidated progress report summarises progress and financial information provided by bilateral and implementing agencies[[2]](#footnote-2) as of 31 December 2020, in their respective progress reports[[3]](#footnote-3) submitted to the Secretariat.

# The consolidated progress report and the progress reports of the bilateral and implementing agencies include all controlled substances under the Montreal Protocol. Given that HFC-related projects and activities have been funded either under the regular contributions to the Multilateral Fund or under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment,[[4]](#footnote-4) the information related to these projects is presented separately, based on the funding source. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in mt CO2-eq.[[5]](#footnote-5)

**Review process by the Secretariat**

# The Secretariat reviewed each of the annual progress reports submitted by bilateral and implementing agencies separately. The review was based on the milestones established for investment and non-investment projects including, *inter alia,* signing of agreements; date of release of first disbursement; status of procurement and installation of equipment; status of services provided, including training of refrigeration technicians and customs officers; level of disbursement of approved funds; the operational and financial completion of the project; and the return of fund balances.

# During the review process, potential issues were identified, *inter alia,* cases where agreements had not been signed; instances where a national ozone officer was not in place; lack of financial progress reports; delayed procurement process; lack of availability of alternative technologies in local markets; and security‑related issues at the country level. All projects with outstanding issues had either low disbursement rates of approved funds or/and required an extension of planned completion dates.

# The Secretariat also had several exchanges with each bilateral and implementing agencies on projects and activities with outstanding issues, where several of the issues were satisfactorily resolved. For those projects and activities where the issues could not be resolved, the proposed recommendations for consideration by the Executive Committee were discussed and agreed with the relevant bilateral or implementing agencies. The projects and activities for which an extension of the completion dates has been requested, are considered in the main documents, while the lists of projects[[6]](#footnote-6) with outstanding issues are contained in Annex I of each progress report of bilateral and implementing agencies. The recommendations will be considered during the discussions of each agency progress report at the 88th meeting.

# In line with decision 84/45(c), the Secretariat identified all the MYA components with implementation delays and informed the relevant bilateral and implementing agencies. The Secretariat’s recommendations are contained in Annex I of each progress report of the bilateral and implementing agencies.

# Scope of the document

# The present document consists of the following parts:

## Part I: Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in the implementation of projects for 2020 and cumulatively since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review of the status of implementation of each ongoing[[7]](#footnote-7) project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, as well as projects with outstanding issues for consideration by the Executive Committee.

## Part II: Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down. It provides a summary on the status of implementation of HFC phase‑down projects funded under the voluntary contributions.

Recommendation

# The document also contains the following annexes:

# Annex I An overview of HFC-related projects and activities, which provides information of all HFC-related projects and activities under the Multilateral Fund, irrespective of the source of funding, at the country level, indicating the status of ratification of the Kigali Amendment and the status of the HFC licensing system.

# Annex II An analysis of the consolidated progress report, which provides aggregated information since the inception of the Multilateral Fund up to 31 December 2020, divided into two parts: Part I, Projects approved under the regular contributions to the Multilateral Fund; and Part II, Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down.

Annex III A report on the HFC-related investment projects and enabling activities for the phase-down of HFCs in Article 5 countries (“enabling activities”) funded using the additional contributions by a group of 17 non-Article 5 Parties, which provides a comprehensive progress report on HFC activities funded using the additional contributions, in line with decision 84/12(b) and (c).

# The progress reports of bilateral or implementing agencies did not include any policy issue for consideration by the Executive Committee. Also, no policy issues were identified during the Secretariat’s review of the progress reports.

Part I: Projects approved under the regular contributions to the Multilateral Fund

**Summary of progress in implementation of projects for 2020 and cumulative**

# Implementation of projects and activities by bilateral and implementing agencies for 2020 and cumulative since 1991 up to 31 December 2020, is summarized as follows:

## **Phase-out:** In 2020, 1,324.1[[8]](#footnote-8) ODP tonnes of consumption of controlled substances were phased out and an additional 2,133.4 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 289,191 ODP tonnes and 500,994 mt CO2-eq of consumption and 205,377 ODP tonnes of production of controlled substances had been phased out, of an expected total of 469,653 ODP tonnes and 521,729 mt CO2-eq from projects approved (excluding cancelled and transferred projects);

## **Disbursements/approvals:** In 2020, US $78.64 million was disbursed and US $89.35 million was planned for disbursement based on the 2019 progress report, representing a rate of disbursement of 88 per cent of that planned. Cumulatively, US $3.16 billion had been disbursed out of the total US $3.38 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 93 per cent. In 2020, US $71.9 million was approved for implementation;

## **Cost-effectiveness (in ODP):**[[9]](#footnote-9)Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $8.41/kg. The cost‑effectiveness for the production sector was US $4.62/kg. The average cost‑effectiveness of investment projects per ODP tonne was US $4.87/kg for completed projects and US $50.01/kg for ongoing projects;[[10]](#footnote-10)

## **Number of projects completed:** In 2020, 196 projects were completed. Since 1991, 7,833 projects of the 8,664 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed, representing a completion rate of 90 per cent;

## **Speed of delivery – investment projects:** Projects that were completed in 2020 were completed on average 50 months after their approval. Since 1991, the average time for completion of investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 14 months after they had been approved;

## **Speed of delivery – non-investment projects:** Projects that were completed in 2020 were completed on average 38 months after their approval. Since 1991, the average time for completion of non-investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, 12 months after they had been approved;

## **Project preparation:** Of the 1,751 project preparation activities approved by the end of 2020, 1,629 have been completed, leaving 122 ongoing activities. In 2020, 24 project preparation activities were approved and 36 were completed;

## **Implementation delays:** A total of 831 projects were under implementation at the end of 2020, experiencing, on average, a delay of 14 months. One hundred and nine of these projects are classified as “projects with implementation delays”[[11]](#footnote-11) that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## **MYAs**: In 2020, one MYA for ODS phase-out plan, one MYA for methyl bromide (MB) production, one HFC production phase-out plan, 188 MYAs for HPMPs and one control and phase-out of HFC-23 emissions were under implementation. Since 1991, 404 MYAs have been approved and 212 MYAs have been completed, representing a completion rate of 52 per cent.

Project implementation progress in 2020

# Based on planned completion dates reported in the 2019 progress report, and the results reported in the 2020 progress reports, bilateral and implementing agencies completed 51 per cent of the projects they had planned to complete in 2020 and achieved 19 per cent of the total phase-out target. Two hundred and three of the 550 ongoing projects (excluding IS and project preparation) have revised their planned dates of completion since the 2019 progress report.

# Bilateral and implementing agencies achieved an overall rate of disbursement of 88 per cent in 2020. On a country/region basis, 58 countries (including regions) had a disbursement rate of over 85 per cent while 41 countries had a disbursement rate of below 50 per cent.

# In total, bilateral and implementing agencies are requested to report, at the 90th meeting, on 109 ongoing projects with implementation delays and 53 ongoing projects or tranches of MYAs recommended for status reports.

# Appendix I to Annex II provides information on project implementation on a country basis in 2020, and Appendix II to Annex II summarizes the total funding approved and disbursed for HPMP activities at the country level.

# **Part II: Projects approved under the additional voluntary contributions for fast‑start support for HFC phase-down**

# As of 31 December 2020, the Executive Committee had approved 144 HFC-related projects under the additional voluntary contributions amounting to US $23.93 million (excluding agency support costs). A summary of the status of these projects is presented in Table 1.

# **Table 1. Status of approved HFC-related projects as of the end of 2020**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Type** | **Number of projects** | | | **Funding (US $)\*** | | | |
| **Approved** | **Completed** | **% completed** | **Approved** | **Disbursed** | **Balance** | **% disbursed** |
| Investment\*\* | 6 | 2 | 33 | 8,502,860 | 6,266,199 | 2,236,661 | 74 |
| Project preparation | 10 | 10 | 100 | 273,821 | 214,900 | 58,921 | 78 |
| Technical assistance - Enabling activities | 128 | 22 | 17 | 15,154,254 | 9,842,553 | 5,311,701 | 65 |
| **Total** | **144** | **34** | **24** | **23,930,935** | **16,323,651** | **7,607,284** | **68** |

\*Excludes agency support costs.

\*\* 443.1 mt (678,661 mt CO2-eq) of 754.5 mt (1,108,442 mt CO2-eq.) of HFCs had been phased out.

# Of the 144 projects approved by the end of 2020, two investment projects, 10 preparation of project proposals and 22 enabling activities have been completed. Extension of the completion dates for 106 ongoing enabling activities was approved. The ongoing enabling activities are at various stages of implementation and are expected to be completed between 2021 and 2022. The remaining four ongoing investment projects are expected to be completed in 2021 and 2022. Further to the review process, 20 projects (three investments and 17 enabling activities) are classified as projects with implementation delays and are included in Annex I to the present document containing the Secretariat’s recommendation requesting the submission of a report to the 90th meeting.

# Cumulatively, US $16,323,651 had been disbursed out of the total US $23,930,935 approved for disbursement (excluding agency support costs), representing a disbursement rate of 68 per cent.

# **Secretariat comments**

# The Secretariat noted that due to challenges relating to COVID-19, some of the projects, tranches of HPMPs and HFC phase-down related activities were delayed. In line with decision 82/11(b), extension for these projects up to 31 December 2022 need to be approved by the Executive Committee. The recommendations for the extension of completion dates of HPMPs for Bahamas (the) (UNEP/UNIDO), Cabo Verde (UNEP), Djibouti (UNEP), Fiji (UNEP/UNDP), Kuwait (UNEP/UNIDO), Niger (the) (UNEP/UNIDO), North Macedonia (UNIDO), Pakistan (UNEP/UNIDO) and the Sudan (UNIDO) are addressed as applicable, in the progress reports of the respective implementing agencies, in the document on reports on projects with specific reporting requirements,[[12]](#footnote-12) in the document on tranche submission delays[[13]](#footnote-13) or in the respective project proposal documents. The extension requests for Argentina component of the global chiller replacement project (UNIDO) and enabling activities for Chile (UNIDO), Jordan (UNIDO), Morocco (UNIDO), Papua New Guinea (Germany), Thailand (World Bank) and Uruguay (UNDP/UNIDO) are addressed in the progress reports of the respective implementing agencies.

# The Secretariat notes that the extension of completion dates of HPMPs to beyond 31 December 2022 were requested for Barbados, Botswana, Côte D’Ivoire, Congo (the), Dominica, Grenada, Haiti, Jamaica, Mali, Mozambique, Saint Kitts and Nevis, South Africa, South Sudan, Venezuela (Bolivarian Republic of) and Zambia by the respective implementing agencies; the Secretariat considers that these requests need to be assessed based on a more detailed review and an assessment of the implementation plans to be presented by the respective implementing agencies. Details of the discussion and the recommendation for these projects are presented in the document on the reports on projects with specific reporting requirements.

RECOMMENDATION

# The Executive Committee may wish to note:

## The consolidated progress report of the Multilateral Fund as at 31 December 2020 contained in document UNEP/OzL.Pro/ExCom/88/12;

## With appreciation, the efforts undertaken by bilateral and implementing agencies in reporting their 2020 activities; and

## That the bilateral and implementing agencies would report, at the 90th meeting, on 129 projects with implementation delays and 53 ongoing projects or tranches of multi‑year agreements recommended for additional status reports, as contained in Annex I of each individual progress report of bilateral and implementing agencies.

**Annex I**

**AN OVERVIEW OF HFC-RELATED PROJECTS AND ACTIVITIES**

# Since its 80th meeting, the Executive Committee has approved funding for the implementation of HFC investment projects (decisions 78/3(g) and 79/45), and enabling activities to help national ozone units fulfil their initial obligations with regard to HFC phase-down in line with the Kigali Amendment (decision 79/46).

# As of 31 December 2020, the Executive Committee has approved 184 HFC-related projects and activities in 137 countries, consisting of 13 requests for project preparation, 14 investment projects and 157 enabling activities, amounting to US $32.81 million (excluding support costs).

# Table 1 presents an overview of all HFC-related projects and activities under the Multilateral Fund, irrespective of their source of funding, at the country level, indicating the status of ratification of the Kigali Amendment and the status of the HFC licensing system.

**Table 1. Overview of all HFC-related projects and activities under the Multilateral Fund**

| **Country** | **Group** | **Ratification of Kigali Amendment** | **Implementation of licensing system** | **Funds approved for (US $)** | | |
| --- | --- | --- | --- | --- | --- | --- |
| **Enabling activities** | **Investment projects** | **Preparation projects** |
| Afghanistan | 1 |  |  | 150,000 |  |  |
| Albania | 1 | Yes | √ | 94,978 |  |  |
| Algeria | 1 |  |  | 150,000 |  |  |
| Angola | 1 | Yes | Pending | 150,000 |  |  |
| Antigua and Barbuda | 1 |  |  |  |  |  |
| Argentina | 1 | Yes | √ | 250,000 | 1,840,755 | 74,816 |
| Armenia | 1 | Yes | √ | 150,000 |  |  |
| Bahamas (the) | 1 |  |  | 95,000 |  |  |
| Bahrain | 2 |  |  | 150,000 |  |  |
| Bangladesh | 1 | Yes | √ | 150,000 | 3,131,610 |  |
| Barbados | 1 | Yes | √ |  |  |  |
| Belize | 1 |  |  | 95,000 |  |  |
| Benin | 1 | Yes | √ | 150,000 |  |  |
| Bhutan | 1 | Yes | √ | 50,000 |  |  |
| Bolivia (Plurinational State of) | 1 | Yes | √ | 150,000 |  |  |
| Bosnia and Herzegovina | 1 | Yes | √ | 95,000 |  |  |
| Botswana | 1 | Yes | Pending | 150,000 |  |  |
| Brazil | 1 |  |  |  |  |  |
| Brunei Darussalam | 1 |  |  | 150,000 |  |  |
| Burkina Faso | 1 | Yes | √ | 150,000 |  |  |
| Burundi | 1 | Yes | Pending | 150,000 |  |  |
| Cabo Verde | 1 | Yes | Pending | 95,000 |  |  |
| Cambodia | 1 | Yes | √ | 150,000 |  |  |
| Cameroon | 1 | Yes | Pending | 150,000 |  |  |
| Central African Republic (the) | 1 |  |  |  |  |  |
| Chad | 1 | Yes | √ | 150,000 |  |  |
| Chile | 1 | Yes | √ | 150,000 |  |  |
| China | 1 | Yes | Pending | 250,000 | 1,275,000 | 64,066 |
| Colombia | 1 | Yes | √ | 250,000 |  |  |
| Comoros (the) | 1 | Yes | √ | 50,000 |  |  |
| Congo (the) | 1 |  |  | 150,000 |  |  |
| Cook Islands (the) | 1 | Yes | √ | 50,000 |  |  |
| Costa Rica | 1 | Yes | √ | 150,000 |  |  |
| Côte d'Ivoire | 1 | Yes | Pending | 150,000 |  |  |
| Cuba | 1 | Yes | Pending | 150,000 |  |  |
| Democratic People's Republic of Korea (the) | 1 | Yes | √ |  |  |  |
| Democratic Republic of the Congo (the) | 1 |  |  | 150,000 |  |  |
| Djibouti | 1 |  |  | 50,000 |  |  |
| Dominica | 1 |  |  | 50,000 |  |  |
| Dominican Republic (the) | 1 | Yes | √ | 150,000 | 129,825 | 30,000 |
| Ecuador | 1 | Yes | √ | 150,000 |  | 29,937 |
| Egypt | 1 |  |  | 250,000 |  | 30,000 |
| El Salvador | 1 | Yes | Pending | 150,000 |  |  |
| Equatorial Guinea | 1 |  |  | 150,000 |  |  |
| Eritrea | 1 |  |  | 95,000 |  |  |
| Eswatini | 1 | Yes | Pending | 95,000 |  |  |
| Ethiopia | 1 | Yes | Pending | 95,000 |  |  |
| Fiji | 1 | Yes | √ | 150,000 |  |  |
| Gabon | 1 | Yes | √ | 150,000 |  |  |
| Gambia (the) | 1 | Yes | Pending | 95,000 |  |  |
| Georgia | 1 |  |  | 95,000 |  |  |
| Ghana | 1 | Yes | √ | 150,000 |  |  |
| Grenada | 1 | Yes | √ | 46,491 |  |  |
| Guatemala | 1 |  |  | 150,000 |  |  |
| Guinea | 1 | Yes | √ | 150,000 |  |  |
| Guinea-Bissau | 1 | Yes | Pending | 95,000 |  |  |
| Guyana | 1 |  |  | 95,000 |  |  |
| Haiti | 1 |  |  | 95,000 |  |  |
| Honduras | 1 | Yes | √ | 150,000 |  |  |
| India | 2 |  |  |  |  |  |
| Indonesia | 1 |  |  | 250,000 |  |  |
| Iran (Islamic Republic of) | 2 |  |  | 250,000 |  |  |
| Iraq | 2 |  |  | 250,000 |  |  |
| Jamaica | 1 |  |  | 150,000 |  |  |
| Jordan | 1 | Yes | √ | 150,000 | 1,637,610 |  |
| Kenya | 1 |  |  | 150,000 |  |  |
| Kiribati | 1 | Yes | √ | 50,000 |  |  |
| Kuwait | 2 |  |  | 250,000 |  |  |
| Kyrgyzstan | 1 | Yes | √ | 95,000 |  |  |
| Lao People's Democratic Republic (the) | 1 | Yes | √ | 95,000 |  |  |
| Lebanon | 1 | Yes | √ | 150,000 | 1,053,858 | 30,000 |
| Lesotho | 1 | Yes | Pending | 95,000 |  |  |
| Liberia | 1 | Yes | Pending | 95,000 |  |  |
| Libya | 1 |  |  | 150,000 |  |  |
| Madagascar | 1 |  |  | 150,000 |  |  |
| Malawi | 1 | Yes | √ | 150,000 |  |  |
| Malaysia | 1 | Yes | √ | 250,000 |  |  |
| Maldives | 1 | Yes | √ | 95,000 |  |  |
| Mali | 1 | Yes | Pending | 150,000 |  |  |
| Marshall Islands (the) | 1 | Yes | √ | 50,000 |  |  |
| Mauritania | 1 |  |  | 150,000 |  |  |
| Mauritius | 1 | Yes | √ | 150,000 |  |  |
| Mexico | 1 | Yes | √ | 250,000 | 4,201,181 | 84,818 |
| Micronesia (Federated States of) | 1 | Yes | √ | 50,000 |  |  |
| Mongolia | 1 |  |  | 95,000 |  |  |
| Montenegro | 1 | Yes | √ | 49,973 |  |  |
| Morocco | 1 |  |  | 150,000 |  |  |
| Mozambique | 1 | Yes | Pending | 150,000 |  |  |
| Myanmar | 1 |  |  | 95,000 |  |  |
| Namibia | 1 | Yes | √ | 150,000 |  |  |
| Nauru | 1 |  |  | 50,000 |  |  |
| Nepal | 1 |  |  | 95,000 |  |  |
| Nicaragua | 1 | Yes | √ | 150,000 |  |  |
| Niger (the) | 1 | Yes | √ | 150,000 |  |  |
| Nigeria | 1 | Yes | √ | 250,000 |  |  |
| Niue | 1 | Yes | √ | 50,000 |  |  |
| North Macedonia | 1 | Yes | √ | 95,000 |  |  |
| Oman | 2 |  |  | 150,000 |  |  |
| Pakistan | 2 |  |  | 250,000 |  |  |
| Palau | 1 | Yes | √ | 50,000 |  |  |
| Panama | 1 | Yes | √ | 150,000 |  |  |
| Papua New Guinea | 1 |  |  | 95,000 |  |  |
| Paraguay | 1 | Yes | √ | 150,000 |  |  |
| Peru | 1 | Yes | Pending | 147,582 |  |  |
| Philippines (the) | 1 |  |  | 225,992 |  |  |
| Qatar | 2 |  |  | 150,000 |  |  |
| Republic of Moldova (the) | 1 |  |  | 50,000 |  |  |
| Rwanda | 1 | Yes | √ | 95,000 |  |  |
| Saint Kitts and Nevis | 1 |  |  | 50,000 |  |  |
| Saint Lucia | 1 |  |  | 95,000 |  |  |
| Saint Vincent and the Grenadines | 1 |  |  | 50,000 |  |  |
| Samoa | 1 | Yes | √ | 50,000 |  |  |
| Sao Tome and Principe | 1 | Yes | Pending | 95,000 |  |  |
| Saudi Arabia | 2 |  |  | 250,000 |  |  |
| Senegal | 1 | Yes | Pending | 150,000 |  |  |
| Serbia | 1 |  |  | 150,000 |  |  |
| Seychelles | 1 | Yes | √ | 95,000 |  |  |
| Sierra Leone | 1 | Yes | Pending | 95,000 |  |  |
| Solomon Islands | 1 |  |  | 95,000 |  |  |
| Somalia | 1 | Yes | Pending | 150,000 |  |  |
| South Africa | 1 | Yes | Pending | 240,000 |  |  |
| South Sudan | 1 |  |  | 95,000 |  |  |
| Sri Lanka | 1 | Yes | √ | 150,000 |  |  |
| Sudan (the) | 1 |  |  | 150,000 |  | 30,000 |
| Suriname | 1 |  |  | 95,000 |  |  |
| Syrian Arab Republic | 1 | Yes | Pending | 250,000 |  |  |
| Thailand | 1 |  |  | 250,000 | 183,514 | 30,000 |
| Timor-Leste | 1 |  |  | 50,000 |  |  |
| Togo | 1 | Yes | √ | 150,000 |  |  |
| Tonga | 1 | Yes | √ | 50,000 |  |  |
| Trinidad and Tobago | 1 | Yes | √ | 150,000 |  |  |
| Tunisia | 1 | Yes | Pending | 150,000 |  |  |
| Turkey | 1 |  |  | 250,000 |  |  |
| Turkmenistan | 1 | Yes | √ | 150,000 |  |  |
| Tuvalu | 1 | Yes | √ | 50,000 |  |  |
| Uganda | 1 | Yes | √ | 50,000 |  |  |
| United Republic of Tanzania (the) | 1 |  |  | 95,000 |  |  |
| Uruguay | 1 | Yes | √ | 150,000 |  |  |
| Vanuatu | 1 | Yes | √ | 50,000 |  |  |
| Venezuela (Bolivarian Republic of) | 1 |  |  | 250,000 |  |  |
| Viet Nam | 1 | Yes | √ | 249,238 |  |  |
| Yemen | 1 |  |  |  |  |  |
| Zambia | 1 | Yes | Pending | 95,000 |  |  |
| Zimbabwe | 1 |  |  | 150,000 | 426,954 | 30,000 |
| **Total** |  |  |  | **18,494,254** | **13,880,307** | **433,637** |

**Annex II**

**ANALYSIS OF THE CONSOLIDATED PROGRESS REPORT**

**OF THE MULTILATERAL FUND AS AT 31 DECEMBER 2020**

# This Annex consists of the following two parts:

## Part I: Projects approved under the regular contributions to the Multilateral Fund.

## Part II: Projects approved under the additional voluntary contributions for fast‑start support for HFC phase-down.

Part I: Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2020, the Executive Committee had approved US $3.78 billion[[14]](#footnote-14) to bilateral and implementing agencies as shown in Table 1. In 2020, 259 new projects and activities were approved. This level of funding is expected to result in the phase-out of 469,653 ODP tonnes of ODS consumption and production.

**Table 1. Approved funding by sector and agency as at 31 December 2020 (US $)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sector** | **UNDP** | **UNEP** | **UNIDO** | **World Bank** | **Bilateral** | **Total** |
| Aerosol | 26,054,837 | 882,689 | 34,413,701 | 22,984,030 | 2,051,914 | 86,387,171 |
| Destruction | 3,606,279 | 190,040 | 3,805,540 | 400,000 | 1,526,282 | 9,528,141 |
| Foam | 173,331,512 | 0 | 89,105,490 | 136,339,172 | 8,093,731 | 406,869,904 |
| Halon | 4,996,973 | 767,640 | 1,780,369 | 70,221,038 | 6,147,361 | 83,913,381 |
| Fumigants | 20,081,241 | 2,614,366 | 78,028,741 | 5,837,887 | 18,226,925 | 124,789,159 |
| Multiple sectors | 0 | 0 | 139,440 | 2,341,168 | 0 | 2,480,608 |
| Other | 0 | 0 | 11,317,246 | 5,059,360 | 0 | 16,376,606 |
| Phase-out plan | 361,740,925 | 64,903,487 | 353,091,265 | 202,645,157 | 68,211,986 | 1,050,592,821 |
| Process agent | 1,286,923 | 0 | 6,337,359 | 114,342,497 | 0 | 121,966,779 |
| Production | 1,056,000 | 0 | 51,128,201 | 378,930,190 | 10,000,000 | 441,114,391 |
| Refrigeration | 139,603,919 | 13,872,913 | 182,191,775 | 180,259,970 | 40,910,116 | 556,838,693 |
| Several | 65,479,103 | 263,992,288 | 19,287,372 | 28,969,731 | 4,759,718 | 382,488,212 |
| Solvents | 63,699,997 | 198,860 | 23,247,443 | 10,237,394 | 2,512,738 | 99,896,432 |
| Sterilant | 417,628 | 0 | 0 | 661,227 | 0 | 1,078,855 |
| **Sub-total** | **861,355,337** | **347,422,283** | **853,873,942** | **1,159,228,820** | **162,440,770** | **3,384,321,153** |
| Agency support costs | 117,625,135 | 28,796,104 | 112,890,657 | 120,209,090 | 15,565,729 | 395,086,716 |
| **Total** | **978,980,472** | **376,218,388** | **966,764,599** | **1,279,437,910** | **178,006,500** | **3,779,407,869** |

# A summary of the status of projects implemented, by category, is presented in Table 2.

**Table 2. Status of project implementation by category**

| **Type** | **Number of projects\*** | | | **Funding (US $)\*\*** | | | |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Approved** | **Completed** | **% completed** | **Approved** | **Disbursed** | **Balance** | **% disbursed** |
| Country programme | 165 | 165 | 100 | 7,266,559 | 7,266,559 | 0 | 100 |
| Demonstration | 134 | 132 | 99 | 61,469,136 | 59,959,388 | 1,509,748 | 98 |
| Institutional strengthening (IS) | 1,292 | 1,133 | 88 | 151,925,702 | 133,850,407 | 18,075,295 | 88 |
| Investment | 3,126 | 2,864 | 92 | 2,686,202,301 | 2,533,551,604 | 152,650,697 | 94 |
| Project preparation | 1,751 | 1,629 | 93 | 87,749,694 | 84,021,589 | 3,728,105 | 96 |
| Technical assistance | 1,872 | 1,586 | 85 | 363,900,998 | 311,840,877 | 52,060,121 | 86 |
| Training projects | 324 | 324 | 100 | 25,806,763 | 25,806,763 | 0 | 100 |
| **Total** | **8,664** | **7,833** | **90** | **3,384,321,153** | **3,156,297,187** | **228,023,965** | **93** |

\*Excludes closed and transferred projects.

\*\* Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year.[[15]](#footnote-15) Of the US $3.38 billion approved, US $3.16 billion has been disbursed (including US $78.64 million disbursed in 2020). All projects and activities approved between 1991 and 2007 have now been completed. Approved projects (investment and non-investment) have resulted in the phase-out of 494,568 ODP[[16]](#footnote-16) tonnes of consumption and production of controlled substances. As of 31 December 2020, investment projects representing around US $2.32 billion have been completed, resulting in the permanent phase-out of 475,913 ODP tonnes of controlled substanceswith an overall cost‑effectiveness of US $4.87/kg ODP phased out.

**Table 3. Status of project implementation by year**

| **Year** | **Number of projects\*** | | | **Funding (US $)\*\*** | | | |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Approved** | **Completed** | **% completed** | **Approved** | **Disbursed** | **Balance** | **% disbursed** |
| 1991 | 68 | 68 | 100 | 7,950,771 | 7,950,771 | 0 | 100 |
| 1992 | 176 | 176 | 100 | 41,261,376 | 41,261,376 | 0 | 100 |
| 1993 | 217 | 217 | 100 | 73,198,586 | 73,198,586 | 0 | 100 |
| 1994 | 379 | 379 | 100 | 128,630,290 | 128,630,290 | 0 | 100 |
| 1995 | 355 | 355 | 100 | 111,188,309 | 111,188,309 | 0 | 100 |
| 1996 | 257 | 257 | 100 | 83,813,027 | 83,813,027 | 0 | 100 |
| 1997 | 532 | 532 | 100 | 154,314,938 | 154,314,940 | -1 | 100 |
| 1998 | 422 | 422 | 100 | 99,680,368 | 99,680,367 | 1 | 100 |
| 1999 | 546 | 546 | 100 | 152,710,736 | 152,710,736 | 0 | 100 |
| 2000 | 426 | 426 | 100 | 109,540,523 | 109,540,522 | 1 | 100 |
| 2001 | 427 | 427 | 100 | 130,139,750 | 130,139,751 | -1 | 100 |
| 2002 | 358 | 358 | 100 | 162,045,816 | 162,045,815 | 1 | 100 |
| 2003 | 247 | 247 | 100 | 157,043,468 | 157,043,468 | 0 | 100 |
| 2004 | 271 | 271 | 100 | 162,388,007 | 162,388,008 | 0 | 100 |
| 2005 | 255 | 255 | 100 | 180,276,023 | 180,276,022 | 1 | 100 |
| 2006 | 261 | 261 | 100 | 120,848,004 | 120,762,417 | 85,586 | 100 |
| 2007 | 213 | 213 | 100 | 120,144,867 | 120,084,048 | 60,820 | 100 |
| 2008 | 354 | 353 | 100 | 121,900,010 | 121,871,235 | 28,775 | 100 |
| 2009 | 320 | 318 | 99 | 73,793,821 | 73,075,355 | 718,466 | 99 |
| 2010 | 227 | 223 | 98 | 84,438,275 | 83,387,745 | 1,050,530 | 99 |
| 2011 | 264 | 263 | 100 | 201,999,135 | 198,222,122 | 3,777,013 | 98 |
| 2012 | 182 | 167 | 92 | 101,122,995 | 97,886,875 | 3,236,121 | 97 |
| 2013 | 184 | 179 | 97 | 125,617,302 | 124,063,191 | 1,554,110 | 99 |
| 2014 | 223 | 202 | 91 | 92,524,185 | 89,430,544 | 3,093,641 | 97 |
| 2015 | 379 | 340 | 90 | 160,139,228 | 141,762,893 | 18,376,335 | 89 |
| 2016 | 240 | 179 | 75 | 115,422,196 | 91,695,424 | 23,726,773 | 79 |
| 2017 | 125 | 77 | 62 | 64,220,346 | 56,371,561 | 7,848,785 | 88 |
| 2018 | 271 | 104 | 38 | 122,853,364 | 56,425,190 | 66,428,174 | 46 |
| 2019 | 226 | 17 | 8 | 53,217,538 | 11,538,883 | 41,678,655 | 22 |
| 2020 | 259 | 1 | 0 | 71,897,896 | 15,537,716 | 56,360,180 | 22 |
| **Total** | **8,664** | **7,833** | **90** | **3,384,321,153** | **3,156,297,187** | **228,023,965** | **93** |

\* Excludes closed and transferred projects.

\*\* Excludes agency support costs.

Completed Projects[[17]](#footnote-17)

# Overall, 99.7 per cent of the funds approved for completed investment projects have been disbursed.[[18]](#footnote-18)

**Completed investment projects**

# Table 4 presents information on investment projects that have been completed since 1991. The table presents the data in total, followed by data according to region, sector, implementation characteristics, and disbursement method.

**Table 4. Cumulative completed investment projects**

| **Item** | **Number of projects** | **Approved funds plus adjustment (US $)** | **Per cent of funds disbursed** | **Consump-tion (ODP phased out\*)** | **Production (ODP phased out\*)** | **Average number of months from approval to first disbursement** | **Average number of months from approval to completion** | **Overall cost-effectiveness to the Fund (US $/kg)** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **TOTAL** | **2,864** | **2,319,105,803** | **100** | **271,724** | **204,189** | **14** | **37** | **4.87** |
| **Region** |  |  |  |  |  |  |  |  |
| Africa | 486 | 163,268,189 | 100 | 18,286 | 0 | 12 | 39 | 8.93 |
| Asia and Pacific | 1,525 | 1,681,472,968 | 100 | 210,775 | 184,239 | 16 | 37 | 4.26 |
| Europe | 150 | 71,853,737 | 100 | 8,048 | 175 | 10 | 34 | 8.74 |
| Latin America and Caribbean | 703 | 402,510,909 | 99 | 34,614 | 19,775 | 14 | 37 | 7.40 |
| Global | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| **Sector** |  |  |  |  |  |  |  |  |
| Aerosol | 127 | 82,517,299 | 100 | 27,449 | 0 | 16 | 43 | 3.01 |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 1,003 | 376,083,231 | 100 | 69,420 | 0 | 15 | 34 | 5.42 |
| Fumigants | 123 | 99,900,005 | 100 | 7,993 | 0 | 10 | 49 | 12.50 |
| Halon | 39 | 71,476,177 | 100 | 42,111 | 41,958 | 17 | 30 | 0.85 |
| Multiple sectors | 4 | 2,287,376 | 100 | 419 | 0 | 28 | 78 | 5.46 |
| Other | 8 | 16,059,360 | 100 | 1,574 | 0 | 12 | 20 | 10.20 |
| Phase-out plan | 722 | 600,658,874 | 99 | 51,507 | 10,988 | 12 | 40 | 9.61 |
| Process agent | 30 | 120,252,627 | 100 | 19,573 | 52,162 | 10 | 27 | 1.68 |
| Production | 61 | 414,398,882 | 100 | 0 | 99,081 | 9 | 19 | 4.18 |
| Refrigeration | 616 | 440,046,314 | 100 | 44,334 | 0 | 16 | 39 | 9.93 |
| Solvents | 128 | 94,351,804 | 100 | 7,285 | 0 | 19 | 32 | 12.95 |
| Sterilant | 3 | 1,073,855 | 100 | 60 | 0 | 15 | 34 | 17.78 |
| **Implementation characteristics** | | | | | | | | |
| Agency implementation | 1,774 | 832,724,855 | 100 | 94,262 | 17,381 | 11 | 35 | 7.46 |
| National implementation | 1,090 | 1,486,380,948 | 100 | 177,462 | 186,808 | 20 | 40 | 4.08 |
| **Disbursement method** | | | | | | | | |
| During implementation | 2,753 | 2,004,358,631 | 100 | 264,841 | 199,719 | 14 | 38 | 4.31 |
| After implementation | 50 | 17,166,608 | 100 | 2,512 | 0 | 23 | 25 | 6.83 |
| Retroactive funding | 37 | 14,635,851 | 100 | 2,100 | 500 | 15 | 11 | 5.63 |
| Country to final beneficiaries | 24 | 282,944,713 | 100 | 2,270 | 3,970 | 8 | 51 | 45.34 |

\*Excludes closed and transferred projects.

Completed non-investment projects

# Table 5 presents data on cumulative completed non-investment projects. Since 1991, 3,340 non‑investment projects have been completed at a total value of US $526.93 million.

**Table 5. Cumulative completed non-investment projects**

| **Item** | **Number of projects** | **Approved funds plus adjustment (US $)** | **Per cent of funds disbursed (%)** | **Average number of months from approval to first disbursement** | **Average number of months from approval to completion** |
| --- | --- | --- | --- | --- | --- |
| **TOTAL** | 3,340 | 526,930,493 | 99 | 12 | 38 |
| **Region** |  |  |  |  |  |
| Africa | 1,014 | 87,524,624 | 99 | 11 | 38 |
| Asia and Pacific | 1,003 | 150,297,520 | 99 | 13 | 40 |
| Europe | 219 | 20,783,266 | 100 | 9 | 33 |
| Latin America and Caribbean | 794 | 93,971,221 | 99 | 13 | 41 |
| Global | 310 | 174,353,862 | 97 | 6 | 23 |
| **Sector** |  |  |  |  |  |
| Aerosol | 31 | 2,461,265 | 100 | 11 | 36 |
| Destruction | 16 | 7,205,265 | 100 | 11 | 63 |
| Fire fighting | 0 | 0 | 0 | n/a | n/a |
| Foam | 34 | 10,738,870 | 98 | 14 | 36 |
| Fumigants | 137 | 21,224,434 | 100 | 9 | 39 |
| Halon | 82 | 11,238,156 | 100 | 17 | 44 |
| Multiple sectors | 1 | 53,792 | 100 | 56 | 58 |
| Other | 1 | 76,499 | 100 | 7 | 38 |
| Phase-out plan | 564 | 55,302,572 | 98 | 13 | 41 |
| Process agent | 0 | 0 | 0 | n/a | n/a |
| Production | 1 | 40,000 | 100 | 4 | 4 |
| Refrigeration | 638 | 91,902,739 | 99 | 16 | 50 |
| Several | 1,801 | 323,288,119 | 98 | 10 | 32 |
| Solvents | 34 | 3,398,782 | 100 | 11 | 27 |
| Sterilant | 0 | 0 | 0 | n/a | n/a |
| **Implementation Characteristics** |  |  |  |  |  |
| Agency implementation | 2,724 | 398,241,985 | 98 | 11 | 37 |
| National implementation | 616 | 128,688,508 | 99 | 14 | 41 |
| **Disbursement Method** |  |  |  |  |  |
| During implementation | 3,306 | 515,024,296 | 99 | 12 | 38 |
| After implementation | 26 | 2,325,462 | 100 | 14 | 21 |
| Retroactive funding | 1 | 146,698 | 100 | 3 | 83 |
| Country to final beneficiaries | 7 | 9,434,037 | 100 | 7 | 38 |

# The average time from approval to first disbursement for non-investment projects is 12 months. Non-investment projects have been completed, on average, 38 months after they were approved. This figure is influenced by the large number of projects (1,801 of 3,340) in the sector called “several”, which had an average time from approval to completion of 32 months. Non‑investment projects in the other sectors were completed between four and 63 months after they had been approved.

# Almost all projects were implemented by the agency concerned rather than through national implementation. Agency implementation of non-investment projects normally does not require legal agreements, which may explain the shorter period of time (37 months) compared with nationally‑implemented non-investment projects (41 months).

**Ongoing Projects**

## **Ongoing investment projects**

# Table 6 presents information on the status of investment projects under implementation by region, sector, and implementation characteristics.

**Table 6. Cumulative ongoing investment projects**

| **Item** | **Number of projects** | **Approved funds plus adjustment (US $)** | **Per cent of funds disbursed** | **Number of projects disbursing** | **Per cent of projects disbursing** | **Average number of months from approval to first disbursement** | **Average number of months from approval to planned completion** | **Average length of delay in project planned completion** | **Overall cost-effectiveness**  **to the Fund (US$/kg.)\*** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **TOTAL** | **262** | **350,726,061** | **59** | **156** | **60** | **11** | **54** | **32** | **50.01** |
| **Region** |  |  |  |  |  |  |  |  |  |
| Africa | 80 | 30,647,500 | 34 | 50 | 63 | 11 | 56 | 28 | 84.01 |
| Asia and Pacific | 102 | 282,482,116 | 64 | 62 | 61 | 11 | 60 | 44 | 46.18 |
| Europe | 21 | 5,143,646 | 29 | 12 | 57 | 8 | 44 | 29 | 86.30 |
| Latin America and Caribbean | 59 | 32,452,799 | 38 | 32 | 54 | 10 | 45 | 20 | 68.65 |
| Global | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| **Sector** |  |  |  |  |  |  |  |  |  |
| Aerosol | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Foam | 3 | 3,573,740 | 68 | 3 | 100 | 10 | 94 | 72 | 73.53 |
| Fumigants | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Phase-out plan | 252 | 317,825,367 | 57 | 149 | 59 | 11 | 53 | 30 | 47.13 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Production | 3 | 25,273,058 | 79 | 2 | 67 | 12 | 54 | 36 | n/a |
| Refrigeration | 4 | 4,053,896 | 73 | 2 | 50 | 7 | 97 | 71 | 18.34 |
| Solvents | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| **Implementation Characteristics** | | | | | | | | | | |
| Agency implementation | 183 | 216,878,898 | 58 | 126 | 69 | 10 | 60 | 33 | 47.57 |
| National implementation | 79 | 133,847,163 | 60 | 30 | 38 | 13 | 40 | 25 | 54.53 |
| **Disbursement Method** | | | | | | | | | | |
| During implementation | 248 | 163,326,691 | 37 | 142 | 57 | 11 | 53 | 30 | 36.02 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Country to final beneficiaries | 14 | 187,399,370 | 77 | 14 | 100 | 10 | 80 | 53 | 75.60 |

\*Based on the ODS to be phased out according to the proposal.

# There are currently 262 investment projects under implementation at a total value of over US $350.72 million. Around 59 per cent of the funds have already been disbursed. The overall average cost-effectiveness of ongoing investment projects is US $50.01/kg ODP to be phased out. The average number of months from approval to first disbursement is 11 months. The average duration of an ongoing investment project is 54 months. Typically, ongoing investment projects are completed 32 months later than originally planned, which could be considered the average delay.

**Ongoing non-investment projects**

# Table 7 presents information on the status of non-investment projects under implementation by region, sector, and implementation characteristic.

**Table 7. Cumulative ongoing non-investment projects**

| **Item** | **Number of projects** | **Approved funds plus adjustment (US $)** | **Per cent of funds disbursed** | **Number of projects disbursing** | **Per cent of projects disbursing** | **Average number of months from approval to first disbursement** | **Average number of months from approval to planned completion** | **Average length of delay in project planned completion** | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **TOTAL** | **447** | **81,990,312** | **22** | **210** | **47** | **12** | **38** | **11** | |
| **Region** |  |  |  |  |  |  |  |  | |
| Africa | 126 | 14,065,461 | 18 | 47 | 37 | 15 | 34 | 8 | |
| Asia and Pacific | 180 | 36,612,607 | 25 | 92 | 51 | 11 | 42 | 12 | |
| Europe | 27 | 2,669,826 | 36 | 13 | 48 | 7 | 30 | 5 | |
| Latin America and Caribbean | 109 | 17,859,980 | 29 | 57 | 52 | 13 | 40 | 13 | |
| Global | 5 | 10,782,438 | 1 | 1 | 20 | 14 | 20 | 7 | |
| **Sector** |  |  |  |  |  |  |  |  | |
| Aerosol | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Destruction | 1 | 1,490,600 | 89 | 1 | 100 | 13 | 103 | 59 | |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Foam | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Fumigants | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Phase-out plan | 253 | 42,905,669 | 21 | 103 | 41 | 13 | 40 | 10 | |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Production | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Refrigeration | 1 | 808,438 | 13 | 1 | 100 | 14 | 49 | 36 | |
| Several | 192 | 36,785,605 | 20 | 105 | 55 | 12 | 35 | 11 | |
| Solvents | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| **Implementation Characteristics** | | | | | | | | |
| Agency implementation | 362 | 57,196,445 | 20 | 161 | 44 | 13 | 39 | 11 | |
| National implementation | 85 | 24,793,867 | 26 | 49 | 58 | 9 | 38 | 10 | |
| **Disbursement Method** | | | | | | | | | |
| During implementation | 446 | 81,491,112 | 21 | 209 | 47 | 12 | 38 | 11 | |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | |
| Country to final beneficiaries | 1 | 499,200 | 98 | 1 | 100 | 9 | 36 | 12 | |

# There are currently 447 non-investment projects under implementation at a total value of US $81.99 million, with 22 per cent of the funds already disbursed. The average number of months from approval to first disbursement is 12 months. On average, ongoing non-investment projects are completed 38 months from the date of approval, which represents a delay of 11 months.

CLOSED PROJECTS

# Table 8 presents a summary of closed projects.

Table 8. Closed projects summary

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Agency** | **Number of projects** | **Approved funding plus adjustment (US$)** | **Funds disbursed (US $)** | **Balances (US$)** | **Consumption ODP to be phased out** | **Consumption ODP phased out** |
| UNDP | 81 | 6,895,392 | 6,895,392 | 0 | 673 | 636 |
| UNEP | 14 | 21,000 | 21,000 | 0 | 12 | 12 |
| UNIDO | 67 | 6,347,808 | 6,347,806 | 1 | 1,808 | 367 |
| World Bank | 95 | 1,373,519 | 1,373,519 | 0 | 657 | 581 |
| Bilateral | 17 | 227,901 | 227,901 | 0 | 223 | 0 |
| **Total** | **274** | **14,865,620** | **14,865,618** | **1** | **3,373** | **1,595** |

HFC-RELATED ACTIVITIES

# Table 9 presents a summary of HFC-related projects approved under regular contributions.

**Table 9. HFC-related projects approved under regular contributions**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Type** | **Number of projects** | | | | **Funding (US $)\*** | | | | |
| **Approved** | **Completed** | **% completed** | **Approved** | | **Disbursed** | **Balance** | **% disbursed** |
| Investment\*\* | 8 | 5 | 63 | 5,377,447 | | 4,262,650 | 1,114,797 | 79 |
| Project preparation | 3 | 2 | 67 | 159,816 | | 129,510 | 30,306 | 81 |
| Technical assistance - Enabling activities | 29 | 0 | 0 | 3,340,000 | | 1,040,636 | 2,299,364 | 31 |
| **Total** | **40** | **7** | **18** | **8,877,263** | | **5,432,795** | **3,444,468** | **61** |

\*Excludes agency support costs.

# \*\* 320.9 mt (500,994 mt CO2-eq) of 335.4 mt (521,729 mt CO2-eq.) of HFCs had been phased out.

# There are currently 40 HFC-related projects (including eight investment projects, three preparation of project proposals and 29 enabling activities) approved under regular contributions at a total value of US $8,877,263, with US $5,432,795 of the funds already disbursed.

# Of the 40 projects, five investment projects and two preparation of a project proposal have been completed. Extension of the completion dates for 29 enabling activities was approved. The ongoing enabling activities are progressing at various stages of implementation and are expected to be completed in 2021 and 2022. The remaining three ongoing investment projects are expected to be completed between 2022 and 2023 and the remaining ongoing project preparation is expected to be completed in 2022.

# **Part II: Projects approved under the additional voluntary contributions for fast‑start support for HFC phase-down**

# As of 31 December 2020, the Executive Committee had approved 144 HFC-related projects under the additional voluntary contributions amounting to US $23.93 million (excluding agency support costs). A summary of the status of these projects is presented in Table 10.

# **Table 10. Status of approved HFC-related projects as of the end of 2020**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Type** | **Number of projects** | | | **Funding (US $)\*** | | | |
| **Approved** | **Completed** | **% completed** | **Approved** | **Disbursed** | **Balance** | **% disbursed** |
| Investment\*\* | 6 | 2 | 33 | 8,502,860 | 6,266,199 | 2,236,661 | 74 |
| Project preparation | 10 | 10 | 100 | 273,821 | 214,900 | 58,921 | 78 |
| Technical assistance - Enabling activities | 128 | 22 | 17 | 15,154,254 | 9,842,553 | 5,311,701 | 65 |
| **Total** | **144** | **34** | **24** | **23,930,935** | **16,323,651** | **7,607,284** | **68** |

\*Excludes agency support costs.

\*\* 443.1 mt (678,661 mt CO2-eq) of 754.5 mt (1,108,442 mt CO2-eq.) of HFCs had been phased out.

# Of the 144 projects approved by the end of 2020, two investment projects, 10 preparation of project proposals and 22 enabling activities have been completed. Extension of the completion dates for 106 ongoing enabling activities was approved. The ongoing enabling activities are at various stages of implementation and are expected to be completed between 2021 and 2022.

# The remaining four ongoing investment projects are expected to be completed in 2021 and 2022. Cumulatively, US $16,323,651 had been disbursed out of the total US $23,930,935 approved for disbursement (excluding agency support costs), representing a disbursement rate of 68 per cent.

Appendix I

PROJECT IMPLEMENTATION IN 2020 BY COUNTRY

| **Country** | **Phased out in 2020\*** | **Percentage of planned phase-out achieved in 2020** | **Estimated funds disbursed in 2020 (US$)** | **Funds disbursed in 2020 (US$)** | **Percentage of funds disbursed over estimation in 2020** | **Percentage of planned projects completed in 2020** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.2 | 0 | 153,693 | 189,669 | 123 | 50 |
| Albania | 0.0 |  | 105,203 | 87,049 | 83 | 100 |
| Algeria | 0.0 |  | 187,220 | 56,864 | 30 | 0 |
| Angola | 0.0 |  | 206,137 | 119,673 | 58 | 0 |
| Antigua and Barbuda | 0.0 |  | 37,812 | 188 | 0 | 0 |
| Argentina | 4.7 | 100 | 796,989 | 874,747 | 110 | 75 |
| Armenia | 0.0 |  | 110,545 | 141,250 | 128 | 100 |
| Bahamas (the) | 0.0 | 0 | 139,847 | 94,603 | 68 | 50 |
| Bahrain | 0.0 |  | 73,621 | 118,525 | 161 | 100 |
| Bangladesh | 0.0 |  | 705,387 | 7,532 | 1 |  |
| Barbados | 0.0 |  | 33,081 | 62,185 | 188 | 100 |
| Belize | 0.0 |  | 10,000 | 47,850 | 479 | 100 |
| Benin | 0.0 | 0 | 75,651 | 107,992 | 143 | 100 |
| Bhutan | 0.0 |  | 125,407 | 66,784 | 53 |  |
| Bolivia (Plurinational State of) | 0.5 |  | 81,216 | 46,152 | 57 | 50 |
| Bosnia and Herzegovina | 0.0 |  | 99,500 | 95,096 | 96 | 0 |
| Botswana | 0.0 | 0 | 212,818 | 116,557 | 55 | 0 |
| Brazil | 20.0 | 0 | 6,784,746 | 3,110,462 | 46 | 50 |
| Brunei Darussalam | 0.2 | 20 | 10,493 | 122,512 | 1168 | 67 |
| Burkina Faso | 0.0 |  | 124,565 | 130,257 | 105 |  |
| Burundi | 0.0 | 0 | 26,000 | 117,455 | 452 | 50 |
| Cambodia | 0.0 |  | 150,186 | 174,782 | 116 |  |
| Cameroon | 0.1 |  | 73,651 | 34,355 | 47 |  |
| Cabo Verde | 0.0 | 0 | 0 | 58,808 | Over | 67 |
| Central African Republic (the) | 0.0 |  | 18,000 | 0 | 0 | 0 |
| Chad | 0.0 | 0 | 26,250 | 20,000 | 76 | 50 |
| Chile | 5.7 | 0 | 609,674 | 441,788 | 72 | 0 |
| China | 831.5 | 6 | 23,648,546 | 33,865,817 | 143 | 27 |
| Colombia | 26.0 | 13 | 964,254 | 392,820 | 41 | 60 |
| Comoros (the) | 0.0 |  | 72,952 | 96,709 | 133 | 100 |
| Congo (the) | 0.0 | 0 | 85,250 | 88,165 | 103 | 0 |
| Cook Islands (the) | 0.0 |  | 51,038 | 79,492 | 156 | 50 |
| Costa Rica | 3.5 |  | 222,542 | 164,696 | 74 | 100 |
| Côte D'Ivoire | 0.1 |  | 209,446 | 33,810 | 16 |  |
| Cuba | 3.2 |  | 223,459 | 289,759 | 130 | 50 |
| Democratic People's Republic of Korea (the) | 0.0 |  | 4 | 21,485 | 537121 |  |
| Democratic Republic of the Congo (the) | 0.0 |  | 83,819 | 39,900 | 48 | 33 |
| Djibouti | 0.0 |  | 50,846 | 0 | 0 | 0 |
| Dominica | 0.0 |  | 96,875 | 24,546 | 25 | 33 |
| Dominican Republic (the) | 0.0 | 100 | 338,354 | 339,888 | 100 | 50 |
| Ecuador | 7.7 | 0 | 315,725 | 216,835 | 69 | 100 |
| Egypt | 23.1 | 29 | 3,415,272 | 2,307,883 | 68 | 0 |
| El Salvador | 0.0 | 0 | 288,824 | 104,405 | 36 | 50 |
| Equatorial Guinea | 0.0 | 0 | 92,655 | 146,301 | 158 | 50 |
| Eritrea | 0.0 |  | 29,600 | 89 | 0 | 100 |
| Eswatini (the Kingdom of) | 0.0 |  | 64,000 | 45,000 | 70 |  |
| Ethiopia | 0.0 | 0 | 119,545 | 50,000 | 42 | 0 |
| Fiji | 0.0 | 0 | 77,896 | 75,280 | 97 | 67 |
| Gabon | 0.0 |  | 127,004 | 152,124 | 120 | 100 |
| Gambia (the) | 0.0 | 0 | 52,585 | 29,693 | 56 | 75 |
| Georgia | 0.7 |  | 72,547 | 30,189 | 42 | 0 |
| Ghana | 8.5 | 61 | 172,597 | 180,932 | 105 | 75 |
| Grenada | 0.0 | 0 | 48,559 | 1,919 | 4 | 33 |
| Guatemala | 0.8 | 0 | 100,047 | 136,679 | 137 | 50 |
| Guinea | 0.0 |  | 33,698 | 94,930 | 282 | 100 |
| Guinea-Bissau | 0.0 |  | 76,982 | 42,549 | 55 | 67 |
| Guyana | 0.0 |  | 140,679 | 0 | 0 | 100 |
| Haiti | 0.2 |  | 117,329 | 97,061 | 83 | 0 |
| Honduras | 0.0 | 0 | 208,399 | 137,145 | 66 | 80 |
| India | 103.8 | 100 | 7,163,568 | 5,858,631 | 82 | 67 |
| Indonesia | 0.0 | 0 | 1,581,315 | 819,584 | 52 | 60 |
| Iran (Islamic Republic of) | 17.3 | 0 | 2,129,546 | 1,410,533 | 66 | 0 |
| Iraq | 0.0 | 0 | 1,039,828 | 206,524 | 20 | 14 |
| Jamaica | 0.0 | 0 | 145,079 | 65,089 | 45 | 67 |
| Jordan | 118.7 | 0 | 1,384,134 | 1,486,516 | 107 | 50 |
| Kenya | 0.0 |  | 277,152 | 189,179 | 68 | 0 |
| Kiribati | 0.0 |  | 67,519 | 22,429 | 33 | 0 |
| Kuwait | 0.0 |  | 3,774,091 | 3,094,632 | 82 | 0 |
| Kyrgyzstan | 0.5 | 71 | 143,942 | 117,140 | 81 | 67 |
| Lao People's Democratic Republic (the) | 0.0 | 0 | 127,928 | 101,411 | 79 | 100 |
| Lebanon | 6.3 |  | 249,574 | 420,099 | 168 | 100 |
| Lesotho | 0.0 |  | 81,400 | 74,366 | 91 | 50 |
| Liberia | 0.0 |  | 74,629 | 108,527 | 145 |  |
| Libya | 0.0 |  | 171,004 | 92,179 | 54 | 0 |
| Madagascar | 0.0 | 0 | 124,340 | 121,783 | 98 | 100 |
| Malawi | 0.0 | 0 | 45,360 | 34,190 | 75 | 100 |
| Malaysia | 10.0 |  | 634,368 | 834,646 | 132 |  |
| Maldives | 0.0 |  | 72,023 | 37,560 | 52 | 100 |
| Mali | 0.0 |  | 69,630 | 110 | 0 | 0 |
| Marshall Islands (the) | 0.0 | 0 | 92,885 | 42,120 | 45 | 50 |
| Mauritania | 0.0 |  | 186,500 | 135,000 | 72 | 50 |
| Mauritius | 0.0 |  | 153,929 | 181,513 | 118 |  |
| Mexico | 84.8 | 0 | 2,665,699 | 1,176,965 | 44 | 33 |
| Micronesia (Federated States of) | 0.0 | 0 | 69,223 | 61,745 | 89 | 50 |
| Mongolia | 0.0 | 0 | 120,341 | 91,909 | 76 | 100 |
| Montenegro | 0.0 |  | 30,001 | 53,352 | 178 | 100 |
| Morocco | 0.0 |  | 122,000 | 85,655 | 70 | 100 |
| Mozambique | 0.0 |  | 115,183 | 124,079 | 108 | 0 |
| Myanmar | 0.0 | 0 | 189,022 | 46,069 | 24 | 33 |
| Namibia | 0.0 | 0 | 134,672 | 64,231 | 48 | 50 |
| Nauru | 0.0 |  | 25,122 | 17,185 | 68 | 0 |
| Nepal | 0.0 |  | 115,899 | 128,247 | 111 | 100 |
| Nicaragua | 0.8 | 0 | 123,494 | 117,532 | 95 | 67 |
| Niger (the) | 0.0 |  | 129,500 | 3,747 | 3 | 50 |
| Nigeria | 5.2 | 10 | 1,093,923 | 712,562 | 65 | 17 |
| Niue | 0.0 |  | 61,600 | 31,035 | 50 | 0 |
| North Macedonia | 0.1 |  | 75,001 | 115,312 | 154 |  |
| Oman | 0.0 | 0 | 181,970 | 107,989 | 59 | 0 |
| Pakistan | 0.0 |  | 1,940,520 | 408,396 | 21 | 0 |
| Palau | 0.0 | 0 | 80,086 | 5,299 | 7 | 100 |
| Panama | 1.4 | 16 | 321,703 | 263,364 | 82 | 0 |
| Papua New Guinea | 0.0 | 0 | 106,013 | 66,961 | 63 | 0 |
| Paraguay | 0.0 |  | 152,433 | 98,448 | 65 |  |
| Peru | 0.0 |  | 256,036 | 250,765 | 98 |  |
| Philippines (the) | 0.0 |  | 334,920 | 344,917 | 103 |  |
| Qatar | 1.6 | 55 | 66,816 | 99,204 | 148 | 83 |
| Republic of Moldova (the) | 0.0 |  | 118,765 | 80,147 | 67 |  |
| Rwanda | 0.2 | 25 | 115,331 | 82,680 | 72 | 75 |
| Saint Kitts and Nevis | 0.0 | 0 | 72,300 | 0 | 0 | 0 |
| Saint Lucia | 0.0 | 0 | 117,100 | 71,968 | 61 | 25 |
| Saint Vincent and the Grenadines | 0.0 |  | 114,750 | 130,676 | 114 | 33 |
| Samoa | 0.0 | 0 | 94,535 | 65,951 | 70 | 100 |
| Sao Tome and Principe | 0.0 | 0 | 72,462 | 54,076 | 75 | 25 |
| Saudi Arabia | 19.0 |  | 911,624 | 863,317 | 95 | 67 |
| Senegal | 0.0 |  | 92,672 | 150,334 | 162 | 100 |
| Serbia | 0.0 |  | 135,323 | 70,271 | 52 | 50 |
| Seychelles | 0.0 |  | 52,800 | 41,661 | 79 | 0 |
| Sierra Leone | 0.0 |  | 80,822 | 132,565 | 164 | 67 |
| Solomon Islands | 0.0 | 0 | 81,189 | 39,676 | 49 | 50 |
| Somalia | 0.0 |  | 78,000 | 60,125 | 77 | 0 |
| South Africa | 0.0 |  | 163,300 | 119,458 | 73 | 25 |
| South Sudan | 0.0 |  | 39,000 | 0 | 0 | 0 |
| Sri Lanka | 0.0 | 0 | 77,060 | 145,540 | 189 | 100 |
| Sudan (the) | 0.0 |  | 763,145 | 267,969 | 35 | 0 |
| Suriname | 0.1 | 0 | 66,210 | 75,433 | 114 | 33 |
| Syrian Arab Republic | 0.0 |  | 48,001 | 635,147 | 1323 |  |
| Thailand | 0.0 |  | 458,737 | 0 | 0 | 0 |
| Timor-Leste | 0.0 |  | 170,312 | 60,942 | 36 | 100 |
| Togo | 3.6 |  | 185,577 | 230,590 | 124 | 100 |
| Tonga | 0.0 |  | 54,076 | 56,493 | 104 | 50 |
| Trinidad and Tobago | 7.2 |  | 135,972 | 141,914 | 104 |  |
| Tunisia | 5.8 | 0 | 575,550 | 353,312 | 61 | 50 |
| Turkey | 0.0 |  | 784,020 | 814,128 | 104 | 100 |
| Turkmenistan | 0.0 |  | 44,000 | 65,628 | 149 | 100 |
| Tuvalu | 0.0 |  | 67,598 | 2,590 | 4 | 0 |
| Uganda | 0.0 |  | 60,126 | 54,464 | 91 | 75 |
| United Republic of Tanzania (the) | 0.0 | 0 | 110,243 | 29,225 | 27 | 33 |
| Uruguay | 1.0 | 100 | 308,885 | 319,339 | 103 | 100 |
| Vanuatu | 0.0 | 0 | 132,345 | 54,267 | 41 | 50 |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 134,681 | 61,606 | 46 |  |
| Viet Nam | 0.0 | 0 | 1,867,212 | 428,133 | 23 | 0 |
| Yemen | 0.0 |  | 51,000 | 0 | 0 | 0 |
| Zambia | 0.0 | 0 | 81,405 | 88,280 | 108 | 100 |
| Zimbabwe | 0.0 |  | 266,813 | 152,122 | 57 |  |
| Global | 0.0 |  | 9,161,399 | 6,519,573 | 71 | 100 |
| Region: ASP | 0.0 |  | 329,144 | 99,972 | 30 | 100 |
| Region: EUR | 0.0 |  | 200,000 | 362,092 | 181 |  |
| **Grand Total** | **1,324.1** | **19** | **89,353,425** | **78,639,627** | **88** | **51** |

\*203.5 mt (332,848 mt CO2-eq.) phased out in 2020 for HFC-related projects.

Appendix II

HCFC PHASE-OUT MANAGEMENT PLAN BY COUNTRY   
AS AT 31 DECEMBER 2020

| **Country** | **Approved phase‑out**  **(ODP tonnes)** | **Funds approved (US$)** | **Funds disbursed (US$)** | **Balance (US$)** | **Funds disbursed (%)** |
| --- | --- | --- | --- | --- | --- |
| Afghanistan | 9.4 | 989,524 | 503,649 | 485,875 | 51 |
| Albania | 2.1 | 440,813 | 283,415 | 157,398 | 64 |
| Algeria | 13.5 | 1,808,804 | 1,192,850 | 615,954 | 66 |
| Angola | 5.6 | 625,726 | 506,636 | 119,090 | 81 |
| Antigua and Barbuda | 0.0 | 27,235 | 27,235 | 0 | 100 |
| Argentina | 142.4 | 15,348,626 | 11,407,995 | 3,940,631 | 74 |
| Armenia | 3.5 | 678,536 | 616,775 | 61,761 | 91 |
| Bahamas (the) | 1.6 | 277,050 | 223,058 | 53,992 | 81 |
| Bahrain | 9.4 | 993,125 | 813,126 | 179,999 | 82 |
| Bangladesh | 32.3 | 4,052,216 | 1,550,586 | 2,501,630 | 38 |
| Barbados | 1.3 | 250,178 | 179,771 | 70,407 | 72 |
| Belize | 1.0 | 236,000 | 236,000 | 0 | 100 |
| Benin | 8.3 | 565,828 | 565,819 | 9 | 100 |
| Bhutan | 0.3 | 423,000 | 384,955 | 38,045 | 91 |
| Bolivia (Plurinational State of) | 1.5 | 314,548 | 278,488 | 36,060 | 89 |
| Bosnia and Herzegovina | 6.6 | 908,645 | 851,833 | 56,812 | 94 |
| Botswana | 3.8 | 810,000 | 305,810 | 504,190 | 38 |
| Brazil | 485.9 | 41,750,640 | 30,549,019 | 11,201,621 | 73 |
| Brunei Darussalam | 1.8 | 475,100 | 268,860 | 206,240 | 57 |
| Burkina Faso | 3.9 | 628,630 | 557,072 | 71,558 | 89 |
| Burundi | 1.0 | 296,844 | 218,730 | 78,114 | 74 |
| Cambodia | 2.9 | 1,150,000 | 1,006,157 | 143,843 | 87 |
| Cameroon | 26.8 | 1,654,770 | 1,190,130 | 464,640 | 72 |
| Cabo Verde | 0.1 | 159,834 | 143,834 | 16,000 | 90 |
| Central African Republic (the) | 0.5 | 64,001 | 64,000 | 0 | 100 |
| Chad | 5.7 | 489,542 | 484,522 | 5,020 | 99 |
| Chile | 72.5 | 5,132,478 | 3,843,194 | 1,289,284 | 75 |
| China | 5,267.3 | 396,859,178 | 342,557,083 | 54,302,095 | 86 |
| Colombia | 189.2 | 11,706,162 | 9,396,862 | 2,309,300 | 80 |
| Comoros (the) | 0.0 | 143,777 | 128,464 | 15,313 | 89 |
| Congo (the) | 3.6 | 313,626 | 240,222 | 73,404 | 77 |
| Democratic Republic of the Congo (the) | 5.8 | 475,000 | 474,524 | 476 | 100 |
| Cook Islands (the) | 0.0 | 264,050 | 73,750 | 190,300 | 28 |
| Costa Rica | 19.6 | 1,341,299 | 1,135,110 | 206,189 | 85 |
| Côte D'Ivoire | 22.3 | 1,638,362 | 657,767 | 980,595 | 40 |
| Croatia | 8.1 | 804,104 | 804,104 | 0 | 100 |
| Cuba | 19.3 | 2,007,527 | 1,685,206 | 322,321 | 84 |
| Djibouti | 0.2 | 143,500 | 99,500 | 44,000 | 69 |
| Dominica | 0.1 | 148,050 | 10,026 | 138,024 | 7 |
| Dominican Republic (the) | 12.5 | 3,840,636 | 2,717,187 | 1,123,449 | 71 |
| Ecuador | 28.0 | 2,681,406 | 2,050,936 | 630,469 | 76 |
| Egypt | 281.7 | 19,971,454 | 9,770,055 | 10,201,398 | 49 |
| El Salvador | 8.8 | 1,072,601 | 884,745 | 187,856 | 82 |
| Equatorial Guinea | 0.9 | 249,962 | 238,600 | 11,361 | 95 |
| Eritrea | 0.4 | 209,559 | 188,559 | 21,000 | 90 |
| Eswatini (the Kingdom of) | 8.3 | 971,931 | 821,931 | 150,000 | 85 |
| Ethiopia | 1.9 | 314,771 | 182,191 | 132,580 | 58 |
| Fiji | 2.0 | 315,000 | 259,289 | 55,711 | 82 |
| Gabon | 10.6 | 480,883 | 396,423 | 84,460 | 82 |
| Gambia (the) | 0.6 | 399,497 | 178,776 | 220,721 | 45 |
| Georgia | 2.3 | 500,900 | 368,329 | 132,571 | 74 |
| Ghana | 26.3 | 1,356,311 | 1,180,952 | 175,359 | 87 |
| Grenada | 0.3 | 189,000 | 174,389 | 14,611 | 92 |
| Guatemala | 5.1 | 597,663 | 366,544 | 231,119 | 61 |
| Guinea | 2.6 | 523,053 | 298,053 | 225,000 | 57 |
| Guinea-Bissau | 1.0 | 278,999 | 221,035 | 57,963 | 79 |
| Guyana | 0.7 | 412,995 | 226,739 | 186,256 | 55 |
| Haiti | 0.4 | 167,119 | 105,093 | 62,027 | 63 |
| Honduras | 8.8 | 841,455 | 526,077 | 315,378 | 63 |
| India | 1,067.4 | 57,607,652 | 32,522,283 | 25,085,369 | 56 |
| Indonesia | 176.9 | 14,757,354 | 11,648,139 | 3,109,215 | 79 |
| Iran (Islamic Republic of) | 297.6 | 18,969,071 | 12,995,507 | 5,973,564 | 69 |
| Iraq | 15.0 | 1,180,000 | 386,789 | 793,211 | 33 |
| Jamaica | 8.9 | 763,899 | 515,699 | 248,200 | 68 |
| Jordan | 59.3 | 5,836,874 | 3,830,053 | 2,006,821 | 66 |
| Kenya | 14.1 | 1,973,000 | 1,096,256 | 876,744 | 56 |
| Kiribati | 0.0 | 310,600 | 82,259 | 228,341 | 26 |
| Democratic People’s Republic of Korea (the) | 19.4 | 804,255 | 271,048 | 533,207 | 34 |
| Kuwait | 209.9 | 8,555,223 | 6,257,331 | 2,297,892 | 73 |
| Kyrgyzstan | 3.3 | 799,922 | 568,846 | 231,076 | 71 |
| Lao People's Democratic Republic (the) | 0.8 | 493,400 | 200,500 | 292,900 | 41 |
| Lebanon | 68.7 | 6,439,571 | 5,695,048 | 744,523 | 88 |
| Lesotho | 0.0 | 280,000 | 228,562 | 51,438 | 82 |
| Liberia | 2.0 | 315,000 | 282,777 | 32,223 | 90 |
| Libya | 26.4 | 1,161,310 | 705,783 | 455,527 | 61 |
| Madagascar | 6.0 | 558,434 | 497,472 | 60,962 | 89 |
| Malawi | 3.8 | 628,745 | 319,248 | 309,498 | 51 |
| Malaysia | 216.5 | 13,866,383 | 12,130,650 | 1,735,733 | 87 |
| Maldives | 0.6 | 1,081,616 | 1,056,580 | 25,036 | 98 |
| Mali | 5.2 | 500,830 | 434,723 | 66,107 | 87 |
| Marshall Islands (the) | 0.2 | 187,200 | 86,545 | 100,655 | 46 |
| Mauritania | 0.0 | 255,000 | 50,000 | 205,000 | 20 |
| Mauritius | 3.1 | 782,500 | 405,989 | 376,511 | 52 |
| Mexico | 555.7 | 27,030,479 | 21,713,553 | 5,316,925 | 80 |
| Micronesia (Federated States of) | 0.2 | 314,100 | 86,489 | 227,611 | 28 |
| Republic of Moldova (the) | 0.3 | 259,759 | 221,793 | 37,966 | 85 |
| Mongolia | 1.0 | 583,769 | 311,615 | 272,154 | 53 |
| Montenegro | 0.6 | 698,389 | 372,392 | 325,997 | 53 |
| Morocco | 11.0 | 1,284,159 | 1,151,968 | 132,191 | 90 |
| Mozambique | 3.1 | 302,361 | 157,990 | 144,371 | 52 |
| Myanmar | 0.4 | 280,000 | 164,800 | 115,200 | 59 |
| Namibia | 8.2 | 810,000 | 605,978 | 204,022 | 75 |
| Nauru | 0.0 | 139,450 | 49,915 | 89,535 | 36 |
| Nepal | 0.7 | 428,000 | 171,641 | 256,359 | 40 |
| Nicaragua | 3.3 | 474,498 | 266,792 | 207,705 | 56 |
| Niger (the) | 5.6 | 488,840 | 273,840 | 215,000 | 56 |
| Nigeria | 143.7 | 7,971,335 | 5,316,926 | 2,654,409 | 67 |
| Niue | 0.0 | 114,200 | 57,225 | 56,975 | 50 |
| North Macedonia | 2.1 | 1,047,130 | 935,263 | 111,867 | 89 |
| Oman | 10.6 | 905,831 | 698,208 | 207,623 | 77 |
| Pakistan | 150.3 | 10,792,366 | 6,419,574 | 4,372,792 | 59 |
| Palau | 0.2 | 303,000 | 103,000 | 200,000 | 34 |
| Panama | 11.6 | 1,264,695 | 660,310 | 604,385 | 52 |
| Papua New Guinea | 2.0 | 991,000 | 760,956 | 230,044 | 77 |
| Paraguay | 6.3 | 630,000 | 525,386 | 104,614 | 83 |
| Peru | 9.5 | 967,497 | 627,189 | 340,308 | 65 |
| Philippines (the) | 40.0 | 3,628,365 | 2,765,925 | 862,439 | 76 |
| Qatar | 14.7 | 1,124,747 | 1,016,441 | 108,306 | 90 |
| Rwanda | 1.9 | 437,399 | 219,063 | 218,336 | 50 |
| Saint Kitts and Nevis | 0.3 | 147,600 | 98,342 | 49,258 | 67 |
| Saint Lucia | 0.4 | 184,418 | 175,218 | 9,200 | 95 |
| Saint Vincent and the Grenadines | 0.2 | 421,951 | 252,365 | 169,586 | 60 |
| Samoa | 0.2 | 344,450 | 139,650 | 204,800 | 41 |
| Sao Tome and Principe | 0.1 | 155,012 | 123,088 | 31,924 | 79 |
| Saudi Arabia | 353.5 | 9,411,617 | 7,128,373 | 2,283,244 | 76 |
| Senegal | 3.6 | 624,023 | 451,328 | 172,695 | 72 |
| Serbia | 5.2 | 1,110,641 | 931,807 | 178,834 | 84 |
| Seychelles | 1.4 | 540,000 | 351,375 | 188,625 | 65 |
| Sierra Leone | 0.4 | 207,620 | 175,475 | 32,145 | 85 |
| Solomon Islands | 1.8 | 466,250 | 148,250 | 318,000 | 32 |
| Somalia | 1.8 | 353,746 | 320,332 | 33,414 | 91 |
| South Africa | 100.3 | 6,354,796 | 5,001,143 | 1,353,653 | 79 |
| South Sudan | 0.0 | 20,000 | 0 | 20,000 | 0 |
| Sri Lanka | 10.1 | 1,064,866 | 593,522 | 471,344 | 56 |
| Sudan (the) | 47.5 | 4,203,396 | 2,246,789 | 1,956,607 | 53 |
| Suriname | 0.6 | 186,742 | 142,109 | 44,633 | 76 |
| Syrian Arab Republic | 10.1 | 590,036 | 0 | 590,036 | 0 |
| United Republic of Tanzania (the) | 0.6 | 209,875 | 151,025 | 58,849 | 72 |
| Thailand | 255.0 | 18,424,008 | 16,924,008 | 1,500,000 | 92 |
| Timor-Leste | 0.0 | 404,700 | 307,674 | 97,026 | 76 |
| Togo | 7.0 | 566,894 | 534,369 | 32,525 | 94 |
| Tonga | 0.1 | 324,050 | 89,723 | 234,327 | 28 |
| Trinidad and Tobago | 17.9 | 1,930,889 | 1,320,477 | 610,412 | 68 |
| Tunisia | 16.8 | 1,837,155 | 1,025,579 | 811,576 | 56 |
| Turkey | 410.7 | 12,427,419 | 9,857,428 | 2,569,991 | 79 |
| Turkmenistan | 2.4 | 812,797 | 622,105 | 190,692 | 77 |
| Tuvalu | 0.1 | 168,450 | 68,063 | 100,387 | 40 |
| Uganda | 0.0 | 287,375 | 140,375 | 147,000 | 49 |
| Uruguay | 15.2 | 1,835,762 | 995,747 | 840,015 | 54 |
| Vanuatu | 0.3 | 360,600 | 130,406 | 230,194 | 36 |
| Venezuela (Bolivarian Republic of) | 28.9 | 2,488,281 | 2,285,131 | 203,150 | 92 |
| Viet Nam | 149.1 | 10,894,762 | 8,707,714 | 2,187,048 | 80 |
| Yemen | 11.6 | 159,529 | 159,529 | 0 | 100 |
| Zambia | 2.5 | 462,956 | 202,956 | 260,000 | 44 |
| Zimbabwe | 12.3 | 1,288,818 | 895,969 | 392,849 | 70 |
| Region: ASP | 0.0 | 940,000 | 240,000 | 700,000 | 26 |
| **Total** | **11,438.5** | **815,362,210** | **637,531,800** | **177,830,411** | **78** |

Annex III

report on the HFC-related investment projects and enabling activities funded using the additional contributions by a group of 17 non‑Article 5 Parties

**Background**

# At its 84th meeting, in considering the Consolidated progress report of the Multilateral Fund as at 31 December 2018, the Executive Committee requested the Secretariat to submit, at the 85th meeting, an additional report on the HFC-related investment projects and enabling activities funded using the additional contributions by a group of 17 non-Article 5 Parties, identifying the countries for which the projects had been approved and providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, on the understanding that that information would be provided on an individual basis for the HFC-related investment projects and on an aggregated basis for the HFC enabling activities (decision 84/12(b)).

# In response to decision 84/12(b), the Secretariat submitted to the 85th meeting[[19]](#footnote-19) the additional report on the HFC-related investment projects and enabling activities using the updated format after incorporating relevant suggestions by the bilateral and implementing agencies.

# Updated information on the HFC-related investment projects and enabling activities using the updated information submitted by the bilateral and implementing agencies is presented below.

**Report on the HFC-related investment projects**

# The implementing agencies provided detailed status reports on the implementation of HFC-related investment projects for Argentina, Bangladesh, China, Lebanon, Mexico, and Thailand. Table 1 provides a summary of the individual projects.

**Table 1. Summary of HFC-related investment projects**

| **Country** | **Agency** | **Products** | **HFC used (mt)** | **Alternative used** | **Mt CO2‑eq** | **Funds approved (US $)** | **Funds disbursed (US $)** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Argentina | UNIDO | Domestic and commercial refrigerators | HFC-134a (96.60 mt) | R-600a/R-290 | 138,069 | 1,840,755 | 1,072,038 |
| Bangladesh | UNDP | Domestic refrigerators and compressors | HFC-134a (230.63 mt) | R-600a | 329,801 | 3,131,610 | 3,131,610 |
| China | UNDP | Domestic refrigerator insulation foam | Cyclopentane + HFC-245fa (250.00 mt) | Cyclopentane + HFO-1233zd(E) | 257,500 | 1,275,000 | 1,018,413 |
| Lebanon | UNIDO | Domestic and commercial refrigerators | HFC-134a/ R‑404A (112.58 mt) | R-600a/R-290 | 245,860 | 1,053,858 | 1,035,787 |
| Mexico | UNIDO | Commercial refrigerators | HFC-134a/ R‑404A (56.04 mt) | R-600a/R-290 | 124,657 | 1,018,123 | 8,351 |
| Thailand[[20]](#footnote-20) | World Bank | Commercial refrigerators | HFC-134a  (8.78 mt) | R-600a | 12,555 | 183,514 | 0 |
| **Total** |  |  | **754.64** |  | **1,108,442** | **8,502,860** | **6,266,199** |

# Two projects (Bangladesh and Lebanon) have been completed; a detailed project report for Bangladesh has been provided by UNDP and the report for Lebanon is expected to be submitted by UNIDO. While the remaining four projects are at advanced stages of completion, COVID-19 situation has resulted in delays relating to final installation, commissioning and training activities for factory personnel; implementing agencies are taking steps to complete these projects before 31 March 2022.

**Report on enabling activities for HFC phase-down**

# The Article 5 countries that received funding for enabling activities for HFC phase-down are listed in Annex I to the present document, along with the status of ratification of the Kigali Amendment and the status of the HFC licensing system as required under Article 4B. The main objectives of the requests for funding enabling activities included *inter alia* support for early ratification of the Kigali Amendment; implementation of activities identified in paragraph 20 of decision XXVIII/2 aimed at initiating supporting institutional arrangements, the review of licensing systems, data reporting on HFC consumption and production, and demonstration of non‑investment activities such as training and information outreach.

Overview of project implementation progress

# Enabling activities are progressing well in almost all countries. So far, the Government of Italy,[[21]](#footnote-21) IBRD,[[22]](#footnote-22) UNDP,[[23]](#footnote-23) UNEP,[[24]](#footnote-24) and UNIDO,[[25]](#footnote-25) have completed 23 projects relating to enabling activities by 2021; despite the challenges imposed by COVID-19, the agencies are working with the countries to ensure expeditious completion of enabling activities.

# A summary of the activities reported is given below:

## Ratification of the Kigali Amendment: Stakeholders consultations on provisions of the Kigali Amendment and implications of its ratification; drafting legal documents; coordination and information outreach to different stakeholders; country assessment on HFC consumption trends and the impact of the Amendment on different stakeholders; training needs assessment for the servicing sector on the introduction of HFC‑free technologies and safe use of alternative technologies and customs officers on monitoring and controlling of HFC trade under the Kigali Amendment; and participation in regional workshop on Kigali Amendment ratification;

## Development and enforcement of licensing and quota system: Review and/or revision of legislations and regulations, including the import/export licensing and quota system, to include Kigali Amendment provisions; consultative workshops on development of licensing[[26]](#footnote-26) and quota system; and consultations on mechanisms for monitoring HFC supply and use in cooperation with customs and other stakeholders;

## Support for enforcement of data collection and monitoring system:Development of a data collection system for HFCs; consultations with importers, traders and other stakeholders on data collection for HFCs and HFC blends; reporting and monitoring requirements; updating the Harmonized System (HS) codes for monitoring HFCs and HFC blends; regional coordination on establishing HS codes for HFCs; and procurement of equipment for identification of HFC refrigerants;

## Implementation of other activities including demonstration and training: Training programmes for using low-global-warming potential (GWP) alternatives including flammable refrigerants with technical expert support; outreach programmes for public awareness on the Kigali Amendment, HFCs and HFC-free alternatives used in different applications, use of low-GWP alternatives, regulatory controls on the use of HFCs/HFC‑free alternatives and monitoring use of HFCs/HFC-free substances, for the manufacturing and/or refrigeration servicing sector, Government and technical institutions and the public; and differential taxation based on GWP of refrigerants; and

## Energy efficiency (EE) related activities: Coordination with EE institutions to include Kigali Amendment provisions while implementing energy efficient measures (e.g., minimum energy performance standards (MEPS), labelling programmes, EE improvement for refrigeration and air-conditioning (RAC) equipment, participation in cooling plans development to promote low-GWP energy efficient technologies, inputs during regional standards development on adopting energy efficient technologies)[[27]](#footnote-27); encouraging participation of EE stakeholders in meetings related to the Kigali Amendment; promoting EE relating to cooling in sectoral EE promotion measures; training on energy efficient RAC technologies; demonstrating savings to the users through the adoption of energy efficient equipment; and design of energy efficient RAC equipment and measures to enhance adoption of energy efficient technologies.

Key finding and lessons learned

# During the implementation of enabling activities, countries gained experience on the Kigali Amendment ratification process and implementation of HFC phase-down enabling activities as summarized below:

## Country assessment report for understanding HFC consumption trends helps stakeholders identify actions to be taken and their responsibilities in implementing these actions and provides recommendations for policy measures and technical assistance activities which would be used as a country roadmap for the implementation of the Kigali Amendment; guidelines on data collection methodologies and structured survey questionnaires/report templates were prepared and communicated to all stakeholders involved; activities relating to cooling action plans and EE improvement with support from funding sources outside the Multilateral Fund also present opportunities for coordination and collaboration for project implementation to phase down HFCs; and interfaces with existing and planned HCFC phase-out management plans (HPMP) activities were internalized through analysis of the levels of consumption of HCFCs and HFCs, and consultations with industry stakeholders;

## Strengthening licensing and quota system to include HFCs and HFC blends is a priority action for monitoring and reporting, which requires detailed consultations with relevant institutions; steps are being taken to ensure proper identification of HFCs and HFC blends, including finalisation of HS Codes and establishing a methodology/processes for accurate HFC data collection and reporting; implementation of online systems are appreciated by customs officers and importers, as it saves them time, costs and efforts; additional capacity building and training of officials handling data collection and monitoring is also a priority action; and customs and enforcement training and strengthening border control points with identification equipment is essential for preventing illegal trade of HFCs;

## Continuous follow-up by the national ozone unit (NOU) with authorities responsible for the drafting, finalization and approval of HFC policies and regulations is essential. Given that HFC‑related activities involve a new set of substances including blends and alternatives that require safe handling, additional efforts are required for capacity building of different national stakeholders for data collection, monitoring and reporting, and for awareness on newly enacted policies and regulations relating to HFCs;

## Significant efforts are required for approval of regulations for adopting low-GWP refrigerants especially relating to safety aspects; capacity building including training and technical information outreach is essential for sustainable adoption of low-GWP refrigerants that are flammable, toxic and operate under high pressure; and capacity building of training and technical institutions, and training and certification of service technicians for handling low-GWP refrigerants are essential; harnessing synergies with the existing activities under HPMPs can facilitate the introduction of sustainable and cost‑effective alternative low-GWP technologies;

## Introduction of MEPS, a progressive tax/duty system based on the EE of non‑HFC‑based RAC equipment and higher tax for products using high-GWP refrigerants creates incentives for the industry to move towards low‑GWP and better energy efficient equipment; and import of second-hand RAC equipment that have lower EE levels affects the implementation of energy efficiency improvement measures, though several information outreach, and capacity building activities are being implemented to minimise such imports;

## Introduction of the national standard on certification of RAC technicians will contribute to lower emissions of HFCs from refrigeration and air conditioning equipment through good servicing practices and adopt safe practices while servicing equipment with flammable, toxic and high-pressure refrigerants.

## Identification of local expertise for undertaking activities requires the continuous support from the NOU and for capacity building, taking into account country specific consumption needs/trends.

## Activities implemented so far have raised awareness among national stakeholders and the public regarding the importance and benefits of the Kigali Amendment, and provided insights into the HFC consumption patterns and importance of EE while phasing-down HFCs, favouring the engagement of stakeholders for the preparation of KIPs and other interventions for monitoring and controlling HFC consumption.

## Potential challenges

# Some of the key challenges faced during the implementation of enabling activities are given below:

# The COVID‑19 pandemic continues to pose challenges in completing the enabling activities within the timeframe approved in some Article 5 countries, particularly related to in-person stakeholder consultations for *inter alia* development and finalisation of regulations relating to HFCs, ratification of the Kigali Amendment, conclusion of training programmes planned under the project;

# Delays in administrative clearances and approval process for ratification of the Kigali Amendment and finalisation of regulations posed challenges in certain Article 5 countries; close follow-up, support from decision makers in the Government and capacity building and information outreach for Government officials were helpful in addressing delays;

# Difficult political and security situation in a few Article 5 countries resulted in delays in project implementation; and

# During implementation, consultations were held *inter alia* on HFC data collection and reporting requirements, use of HFCs and HFC-free alternatives in different applications (e.g., RAC, polyurethane foam). Providing training and technical support to service technicians for the safe adoption of low-GWP alternatives in the RAC sector was highlighted as an important issue. Implementation of training activities covering safe use of alternatives under the HPMPs has provided support to service technicians of HCFC‑based equipment on safe use of low-GWP alternatives; implementation of regulations and other supportive measures for the safe use of low-GWP refrigerant-based equipment (e.g., national standards for import and use of RAC equipment, end-user incentive programmes for low-GWP refrigerant‑based RAC equipment, certification programmes for service technicians on safe servicing practices) and information outreach and awareness activities undertaken during the HPMP on low‑GWP environment friendly alternatives, have increased awareness of national stakeholders on low-GWP technologies mainly in the RAC sector.

# Due to frequent rotation of customs officers, regular training of these officers is crucial for effective enforcement of the HFC licensing and quota system and monitoring and control of HFCs. The enabling activities have helped Article 5 countries in initiating consultations and implementing some activities relating to monitoring HFC consumption and adopting the use of HFC-free alternatives and have initiated dialogues on approach that needs to be adopted for sustainable and energy efficient cooling while implementing HFC phase-down activities. Specific challenges that need to be addressed when implementing HFC phase-down and synergies that can be harnessed while implementing HCFC phase-out and HFC phase-down in the next few years would be clearer when Article 5 countries undertake HFC phase-down strategy preparation after approval of the guidelines by the Executive Committee.

Funds approved and disbursed

# As of 31 December 2020, the total funds approved for HFC investment projects and enabling activities under the additional contributions by a group of 17 donor countries amounted to US $23,954,943, with a total disbursement of US $16,347,659.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |

1. Online meetings and an intersessional approval process will be held in November and December 2021 due to coronavirus disease (COVID-19). [↑](#footnote-ref-1)
2. Progress reports were submitted by the following agencies: Australia, Canada, France, Germany, Italy, Japan, Spain, UNDP, UNEP, UNIDO and the World Bank (UNEP/OzL.Pro/ExCom/88/13 to UNEP/OzL.Pro/ExCom/88/17). [↑](#footnote-ref-2)
3. The Executive Committee requested that detailed information on a project-by-project basis be made available to Committee members, with a printout available upon request (decision 19/23). The database for the Consolidated Progress Report is provided on the Executive Committee’s intranet in the spreadsheet programme, Microsoft Excel. [↑](#footnote-ref-3)
4. At its 77th meeting, the Executive Committee accepted, with appreciation, the additional contributions announced by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment, noting that such funding was one-time in nature and would not displace donor contributions. The contributing parties are Australia, Canada, Denmark, Finland, France, Germany, Ireland, Italy, Japan, Luxembourg, Netherlands, New Zealand, Norway, Sweden, Switzerland, United Kingdom of Great Britain and Northern Ireland, and United States of America. [↑](#footnote-ref-4)
5. In line with decision 84/12(a)(iv), the measurement for HFCs in mt CO2-eq. is included in the progress reports submitted to the 88th meeting. [↑](#footnote-ref-5)
6. Excluding those that are considered in the relevant project proposal documents, under reports on projects with specific reporting requirements (UNEP/OzL.Pro/ExCom/88/18), or under tranche submission delays (UNEP/OzL.Pro/ExCom/88/21). [↑](#footnote-ref-6)
7. Ongoing projects are all projects that were under implementation as at 31 December 2020. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database. [↑](#footnote-ref-7)
8. Including 203.5 mt (332,848 mt CO2-eq.) phased out in 2020 for HFC-related projects. [↑](#footnote-ref-8)
9. Including 335.4 mt of HFC investment projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved. [↑](#footnote-ref-9)
10. The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies. The cost-effectiveness for MYAs of HCFC phase-out management plan (HPMP) is US $44.06/kg ODP, for stage I of HCFC production phase-out management plan is US $23.93/kg ODP and for stage II of HCFC production phase-out management plan is US $4.16/kg ODP. [↑](#footnote-ref-10)
11. Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61) (as demonstration projects, project preparation, and IS are not subject to those procedures). Pursuant to decision 84/45(c), MYA components are subjected to procedure for cancellation. [↑](#footnote-ref-11)
12. UNEP/OzL.Pro/ExCom/88/18 [↑](#footnote-ref-12)
13. UNEP/OzL.Pro/ExCom/88/21 [↑](#footnote-ref-13)
14. An additional US $142.65 million has been approved for the meetings of the Executive Committee, the operation of the Secretariat, and the Treasurer fees. [↑](#footnote-ref-14)
15. The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non‑investment projects) equally (i.e., an investment project or annual funding tranche of an MYA of US $1 million is considered one project as is a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects. [↑](#footnote-ref-15)
16. Total phase‑out for the Fund includes 475,913 ODP tonnes of controlled substances from completed investment projects, 14,420 ODP tonnes from completed non-investment projects and 4,235 ODP tonnes from ongoing projects. [↑](#footnote-ref-16)
17. Completed projects/activities are defined in decisions 17/22 and 19/23 as projects that have been commissioned and where the ODS addressed has been phased out. A further decision (decision 28/2) extends the definition to cover situations where no further use of CFCs in the sectors covered is in evidence, where an alternative product is being produced (and/or production has begun), and where the equipment using CFCs has been destroyed/dismantled/rendered unusable with respect to ODSs. Work programme activities without an ODS phase‑out are considered completed when the activity is finished (e.g., for a workshop, when it has been conducted). This definition has been applied for HCFC-related projects. [↑](#footnote-ref-17)
18. The reason that 100 per cent of funds have not been disbursed for completed projects is that it may take from six months to one year to finalise accounting records. [↑](#footnote-ref-18)
19. UNEP/OzL.Pro/ExCom/85/9 [↑](#footnote-ref-19)
20. The equipment based on the alternative technology is under production; funds would be disbursed by the end of 2020 to the beneficiary enterprise retroactively, after signing of the agreement between the financial intermediary and the beneficiary. [↑](#footnote-ref-20)
21. Lesotho [↑](#footnote-ref-21)
22. Malaysia and the Philippines [↑](#footnote-ref-22)
23. Costa Rica, Jamaica, Peru and Trinidad and Tobago [↑](#footnote-ref-23)
24. Cambodia, Ghana, Kyrgyzstan, Lebanon, Mongolia, Palau, Tonga and Zimbabwe [↑](#footnote-ref-24)
25. Albania, Armenia, Grenada, Mexico, Montenegro, South Africa, Sudan and Viet Nam [↑](#footnote-ref-25)
26. Each Party shall, by 1 January 2019 or within three months of the date of entry into force of this paragraph for it, whichever is later, establish and implement a system for licensing the import and export of new, used, recycled and reclaimed controlled substances in Annex F. Any Party operating under paragraph 1 of Article 5 that decides it is not in a position to establish and implement such a system by 1 January 2019 may delay taking those actions until 1 January 2021. [↑](#footnote-ref-26)
27. There are several new activities on EE improvement implemented by Governments with/without support from sources outside the Multilateral Fund. These activities are evolving based on national requirements. Thus, the information on types of project is illustrative and not exhaustive. [↑](#footnote-ref-27)