Annex II

Table 1

ANNUAL TRANCHES NOT SUBMITTED TO TWO CONSECUTIVE MEETINGS

| Agency | Country | Sector | Tranche | Reason for delay |
| --- | --- | --- | --- | --- |
| World Bank | Antigua and Barbuda | CFC Phase Out Plan | 2006 | Due to the need to change the work plan, remaining funds from the first tranche, and the need to conduct a verification audit. |
| UNEP | Bahrain | CFC Phase Out Plan | 2008 | Replacement of the Training Institute. |
| UNDP | Bahrain | CFC Phase Out Plan | 2008 | Sufficient funds from approved tranches. |
| UNDP | Cuba | ODS Phase Out Plan | 2008 | Sufficient funds from approved tranches. |
| UNIDO | Egypt | CFC Phase Out Plan | 2009 | Verification in audit not completed in time. |
| UNIDO | Kuwait | ODS Phase Out Plan | 2009 | Delay in signing agreement for lead agency UNEP. |
| UNEP | Kuwait | ODS Phase Out Plan | 2008 | Delay in signing agreement for lead agency UNEP. |
| World Bank | Tunisia | ODS Phase Out Plan | 2008 | Due to lack of verification report. |
| World Bank | Turkey | CFC Phase Out Plan | 2008 | Due to slow level of implementation of existing tranche and lack of verification report. |
| World Bank | Viet Nam | Methyl Bromide | 2008 | No need until the end of 2009 as the methyl bromide agreement will be included as an amendment to the National Phase-out Plan. |
| UNEP | Cape Verde | CFC Phase Out Plan | 2009 | Late arrival of training equipment ordered by country according to UNEP. |
| UNIDO | Congo | ODS Phase Out Plan | 2009 | UNEP as lead agency determined that the UNIDO investment project did not have sufficient progress for approval and did not submit the request. |
| UNEP | Congo | ODS Phase Out Plan | 2009 | UNEP as lead agency determined that the UNIDO investment project did not have sufficient progress for approval and did not submit the request. |
| UNEP | Djibouti | CFC Phase Out Plan | 2009 | UNEP as lead agency determined that the UNDP investment project did not have sufficient progress for approval and did not submit the request. |
| UNIDO | Eritrea | ODS Phase Out Plan | 2009 | ODS legislation not in place. |
| UNEP | Eritrea | ODS Phase Out Plan | 2009 | ODS legislation not in place. |
| UNDP | Guyana | CFC Phase Out Plan | 2009 | Sufficient funds from approved tranches. |
| UNEP | Guyana | CFC Phase Out Plan | 2009 | Sufficient funds from approved tranches. |
| France | Lao, PDR | CFC Phase Out Plan | 2009 | Delay in signing agreement. |
| UNIDO | Qatar | CFC Phase Out Plan |  | Delay in signing agreement for lead agency UNEP. |
| UNEP | Qatar | CFC Phase Out Plan | 2009 | Delay in signing agreement for lead agency UNEP. |

# Table 2

ANNUAL TRANCHES NOT SUBMITTED THAT WERE DUE FOR THE FIRST TIME THIS YEAR FOR SUBMISSION TO THE 58TH MEETING

| Agency | Country | Sector | Tranche | Reason for delay |
| --- | --- | --- | --- | --- |
| UNIDO | Benin | CFC Phase Out Plan | 2009 | UNEP as lead agency determined that the UNIDO investment project did not have sufficient progress for approval and did not submit the request. |
| UNEP | Benin | CFC Phase Out Plan | 2009 | UNEP as lead agency determined that the UNIDO investment project did not have sufficient progress for approval and did not submit the request. |
| UNIDO | Burundi | CFC Phase Out Plan | 2009 | UNEP as lead agency determined that the UNIDO investment project did not have sufficient progress for approval and did not submit the request. |
| UNEP | Burundi | CFC Phase Out Plan | 2009 | UNEP as lead agency determined that the UNIDO investment project did not have sufficient progress for approval and did not submit the request. |
| UNEP | Central African Republic | CFC Phase Out Plan | 2009 | Awaiting French procurement of equipment according to UNEP. |
| France | Central African Republic | CFC Phase Out Plan | 2009 | Insufficient progress made with respect to the implementation of the first tranche due to completion of RMP. |
| Canada | Chile | CFC Phase Out Plan |  | Insufficient progress made with respect to the implementation of the first tranche. |
| UNDP | Grenada | CFC Phase Out Plan | 2008 | Low disbursement of funds from approved tranches. |
| UNEP | Grenada | CFC Phase Out Plan | 2008 | Low disbursement of funds from approved tranches. |
| UNEP | Guatemala | CFC Phase Out Plan | 2009 | Delay in signing agreement. |
| UNIDO | Guinea | CFC Phase Out Plan | 2009 | Due to delay in signature and political situation in the country. |
| UNEP | Guinea | CFC Phase Out Plan | 2009 | Due to delay in signature and political situation in the country. |
| UNEP | Guinea-Bissau | CFC Phase Out Plan | 2009 | Due to delay in signature and political situation in the country. |
| UNIDO | Honduras | CFC Phase Out Plan | 2008 | Low disbursement of funds from approved tranches. |
| UNEP | Honduras | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranches. |
| UNEP | Kyrgyzstan | CFC Phase Out Plan | 2008 | Due to need to revise the plan. |
| UNDP | Kyrgyzstan | CFC Phase Out Plan | 2008 | Sufficient funds from approved tranches. |
| World Bank | Malaysia | ODS Phase Out Plan | 2009 | Time needed for review of request for the final tranche. |
| UNEP | Mozambique | CFC Phase Out Plan | 2009 | Delay in signed UNDP agreement to enable the investment project to start. |
| UNDP | Mozambique | CFC Phase Out Plan | 2009 | Delay in signing agreement. |
| UNEP | Nicaragua | CFC Phase Out Plan | 2009 | Low disbursement of approved tranche. |
| UNEP | Peru | CFC Phase Out Plan | 2009 | Delay in signing agreement. |
| UNDP | Peru | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranches. |
| France | Seychelles | CFC Phase Out Plan | 2009 | Delay in determining activities due to lack of CFC imports for several years. |
| UNEP | Suriname | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranches. |
| UNEP | Swaziland | CFC Phase Out Plan | 2009 | Delay in signing agreement. |
| UNDP | Swaziland | CFC Phase Out Plan | 2009 | Delay in signing agreement. |
| World Bank | Thailand | ODS Phase Out Plan | 2009 | Time required for review of request for the final tranche. |
| France | Uganda | ODS Phase Out Plan | 2009 | Delay due to restructuring of Customs Office that has now been restructured and the project is underway. |